## Sheet1
Step	Page	Changes	Dev	WT	Client
Start PreBoard Tour		No changes
1	Landing Page A	Title in Red	Done
		Left justify title	Done
		All CAP words in Red	Done
		People in Caps, Red	Done
		Revise 2nd line: Replace "We are a diverse…" with "Our goal…"	Done
		Remove Gap between pics andlast sentence	Done
		Reduce photo size by 50%	Done
		Photo Image improvement -Please display pictures in a single horizonal row across the page.	To Do	Offshore :Done
2	Landing Page B	Title in Red	Done
		Change all wording	Done
		Replace wording at top	Incomplete	Offshore :Done
		Client desires to pre-enter EE name (editable). EE ID, Eff date prior to EE having access to tour		Ask Dev: How/when? Can the fields client will complete, then be grayed out/uneditable to EE?
		Change name fields (Legal First Name, Preferrd First Name)	Done
4	Questionaire	Change questions	Done
		Remove FB/Twitter/LI text	Done
5	I-9	Correct inability to type first, last name without space to be accepted	Done	Ask Dev: What happens if i9 is not approved? Who does notification go to? Via email?
6	W4	Add State Form Link	Incomplete	Offshore :changes done on LB
		Add Worksheet Link	Incomplete	Offshore :changes done on LB
		Make all 3 links larger	To Do	Offshore :changes done on LB
		Add wording "To access worksheets…" to yellow box above	Incomplete	Query raised to Diana
7	Notice to EE	Left justify EMPLOYEE	Incomplete	Offshore :Done
		Left justify EMPLOYER	Incomplete	Offshore :Done
		Left justify WAGE INFORMATION	Incomplete	Offshore :Done
		Replace fields with text for the following sections with hand written info found on original (MATT New Hire Packet): EMPLOYER section: Legal Name of Hiring Employer; Is Hiring Employer a Staffing…; Physical Address; Hiring Employer's Telephone #; All fields in WORKERS COMPENSATION section. Employer will need to prepopulate Wage Information at same time as prepopulate Demographic info. See question on Jira WT-610 4/6/16 from Diana.	To Do	Query raised to Diana
		Reduce space between Paid Sick leave bullets and boxes below	Incomplete	change request is not possible
		EE/ER dats boxes populate with current date	To Do	Query raised to Diana
8	Direct Deposit	Remove "Memo" verbiage at top	Done
		Add Mail To info after 2nd paragraph	Done
		Move zip code to right of CA	To Do	Offshore :Done
9	Safety Policy	Entire policy must show		Req in Word format 4/5 - Client trying to obtain.
		Name/Date fields marked manditory	Done
10	Drug & Alcohol Policy	Left justify title	To Do	Offshore :Done
		Reformat to fit whole screen	Done
11	Mobile Device Policy	Remove pdf and show whole policy	Done
		Ensure there are 3 signature fields	Done
		Ensure that all signature fields manditory	To Do	Offshore :Done
		Make list of classifications a bullet list	To Do	Offshore :Done (Applied dash as bullet )
		Correct inconsistent spacing between all sections/headers	To Do	Offshore :Done
12	Cell PhoneOrder	Make 1st drop down manditory field	To Do	Offshore :Done
		Revise whole page to include new verbiage	Done
13	Business Card Order	Add verbiage at top	Done
		Change Name wording	Done
		Make 1st drop down manditory field	To Do	Offshore :Done
		Change LEED wording	Done
		Remove all other fields	Done
14	Benefit Overview	Add wording to botton 'Please take some time…"	Done
		Move new "Please take some time.." to position above links	To Do	Offshore :Done
		Left justify Title	To Do	Offshore :Done
		Ensure bullet points are aligned	To Do	Offshore :Done
		Make links at botton larger, closer together	Incomplete	Offshore :Done
15	Ending Page A	Title in Red	Done

Start OnBoard Tour		No changes
1	On Board Overview	No changes
2	Intro to MATT Culture	Left justify Title	Done
		Title Red	Done
		Unbold bullet text	Done
		Question "What are the Unique…": left justify, blue font, double size	Done
3	Culture Video	Video not showing, no link, no window			Client will check again
4	Video Debrief	Title Red	Done
		Questions: left justify, Blue font, double size	Done
5	Building Your Career	Title Red	Done
		Unbold bullet text	Done
		Add "s" to the word questions in 4th bullet	Done
6	What to Expect	Title Red	Done
		Reduce graph size to 75 or 80%	Done
		Reduce space between graph and last line	Done
7	30-60-90	Title Red	Done
		Reduce graph size to 75 or 80%	Done
8	Our Performance	Title Red	Done
		Title Left justified	Done
		Fix typo "it's" and remove extra space before colon	Incomplete	single quote is not allowed through out the system for security purpose
		Final sentence of 1st paragraph fix to "life-long"	Incomplete	Offshore :Done
		3rd paragraph title fix "Bi-Annually" and add dash after "two times each year"	Incomplete	Offshore :Done
		5th paragraph add semicolon after December	Done
9	Training & Dev	Title Red	Done
		Add wording to Internal Training paragrah	Done
		Remove white space before External Traning paragraph	Incomplete	Offshore :Done
		Make 70+20+10 graphic small and to the right side as in originalMake 70+20+10 graphic small and to the right side as in original	Incomplete	Offshore :Done, kindly review and let us know if the changes need to be reverted
10	Mat & Res	Title Red	Done
		Revise 4th bullet wording	Incomplete	Offshore :Done
		5 Bullet point are to be links	Done
		Add "Click in each…" wording	Incomplete	Offshore :Done
11	Ending page B	Title Red	Done
		Title Left justified	Done
		All Text Left Justified	Done
		Blue font on last sentence	Done
12	Ending Page C	Add this page	Done
13	Employee Usage	No changes

		Ability to navigate back to pre-board tunnel for ongoing editing of W4(Fed, State) for all employees	Add to Home/OnBoard/Quicklinks	Kindly add quick links in employee dashboard for your login
		Ability to navigater back to on-board to view video, career info, etc.	Add to Additional Forms	Query raised to Diana
		Notification of Completion @ 1) Each Stage, 2)Makes Change to W4, 3)Approval of changes?		Query raised to Diana