## Sheet1
Step # | Step Name | Change Summary | Change Detail | Status | Comments | Est Date of Complete | Harbinger Comments
General
Various |  | All Signature Fields are Manditory | Correct Preboard 7 | Done
|  | Links to be same Size and color red as on Preboard Step 4 (W4) | Correct Preboard 8, 14 | Done | Unable to remove as it is necessary for ACA function.
|  | User Name | Need to make Date of Birth and SS# non-manditory in Ben Admin so a user name can be generated after Add EE. ER unable to access this info before EE completes tunnel. | Done
|  | Dummy Password | Need to create a dummy password to be used with WT generated Username since DOB/SS# will not be assessable to ER at time of Add EE | Done
|  | ER Access | Where will ER be able to download forms after complete by EE? (PreBoard 4, 5, 6, 7, 9, 10, 11, 12, 13) | Done
n/a | BenAdmin Add Emp | Non-Manditory | Date of Birth field | Incomplete |  |  | Done
n/a | BenAdmin Demographics | Pre-Populate | Pre-populate BenAmin Demographics page Employee ID with 1st 3 letters of first name, 1st 3 letters of last name, last 2 digits of SS# - After New Hire completes the tunnel | Incomplete |  |  | This would be change request for Matt only. Primary investigation is done on it, once analysis is completed will share ETA by tomorrow. Here, Will update EE id as mentioned in EE table once New hire tunnel is completed and this would be one time change.
n/a | BenAdmin EE Admin | Move | Move I9 eVerify Password Reset from EE Administration to Security | Incomplete |  |  | This would be an enhancement again. This would need in depth analysis , we will try to share the ETA by Friday EOD IST
n/a | BenAdmin EE Admin | Move | Move I9 Approval Status from EE Administration to Review Changes | Incomplete |  |  | Here, We can move only the grid of I9 Approval status to Review changes. This new grid will come only when On Board module is mapped. This would need in depth analysis , we will try to share the ETA by Friday EOD IST
n/a | BenAdmin EE Admin | Move | Move Supervisor Approval from EE Administration to Review Changes | Incomplete |  |  | We can move Supervisor Approval page in review changes page. This new grid will come only when On Board module is mapped. This would need in depth analysis , we will try to share the ETA by Friday EOD IST