## Unfinished Req
PreBoard					Harbinger Comments as on 2-May	Image
Step #	Step Name	Change Summary	Change Detail	Status	Comments	Est Date of Complete
2	Landing Page B Begin PreBoardLanding Page B Begin PreBoard	Add wording at top	Please take the time to complete your demographic information accurately, as this is the basis of your employee record.	Incomplete			This line is already present in Demographic page and visible in Employee flow. Refer to screen shot attached
5	I9	Date box to populate with current date	Remove calendar pop-up. Make field uneditable	Incomplete			Change request, code change will be done , needs Dave approval
6	W4	Date box to populate with current date	Remove calendar pop-up. Make field uneditable	Incomplete			Change request, code change will be done , needs Dave approval
		Make Manditory	Total # of Withholdings	Incomplete			Change request, code change will be done , needs Dave approval
7	Notice to EE	Pre-Populate	Wage Info/Rate of Pay - Pull from BenAdmin Payroll Gross Annual Salary	Incomplete			Rate of Pay is already populating. Refer to screen shot attached
			EE/ER dates boxes populate with current date	Incomplete			Done
9	Safety Policy	Pre-Populate	Signature Date, remove calendar pop-up, make uneditable	Incomplete			Done
		Change Signature box to "Employee Name" field		Incomplete			Already done
10	Drug Policy	Change Signature box to "Employee Name" field		Incomplete			Already done
11	Mobile Device Policy	Pre-Populate	Signature Date (3), remove calendar pop-up, make uneditable	Incomplete			Done
Step #	Step Name	Change Summary	Change Detail	Status	Comments	Est Date of Complete
N/A	Ben Admin Add EE	Make Non-Manditory	Date of Birth, EE ID #	Incomplete			EE ID is non-mandatory, Date of Birth cannot set as non mandatory however for employee login it can be set as editable only other than required. / Please confirm
		Make manditory	Job Title	Incomplete			Tilte cannot be change to mandatory however from EE login can be changed to 'Required'. / Please confirm
	BenAdmin EE Admin	Move	(WT-2141) Move I9 eVerify Password Reset from EE Administration to Security	Incomplete	This would be an enhancement again	Will update with progress on Mon 5/2	Dev Estimates: 20 Hours. / Will be scheduled in sprint 3 starting from 9th May
		Move	(WT-2143) Move I9 Approval Status from EE Administration to Review Changes	Incomplete	We can move only the grid of I9 Approval status to Review changes. / This new grid will come only when On Board module is mapped.	Will update with progress on Mon 5/2	Dev Estimates: 32 Hours. / Will be scheduled in sprint 3 starting from 9th May
		Move	(WT-2144) Move Supervisor Approval from EE Administration to Review Changes	Incomplete	We can move Supervisor Approval page in review changes page. / This new grid will come only when On Board module is mapped.	Will update with progress on Mon 5/2	Dev Estimates: 48 Hours. / Will be scheduled in sprint 3 starting from 9th May
	BenAdmin Payroll	Remove	Current Rate field	Incomplete			Can not delete. Message Base Field can not be deleted displayed. However, No rights can be given to employee login. / Please confirm .
		Add Fields (See PreBoard Step 7 "Notice to EE" Wage Info Section for reference	Rate By (Check Boxes)	Incomplete			Done
			Written Agreement…(verbiage) Yes/No Drop Down	Incomplete			Done
			If Yes…(verbiage) Yes/No Drop Down	Incomplete			Done
			Allowances if any…(Text Box)	Incomplete			Done
	n/a	Admin Notification	(WT-1788) Notification of ER (vyost@mattconstruction.com) when each tour is complete or when forms are changed by EE	Incomplete	Notification to email not possible. Will provide pick-up folder path.	Will update with progress on Mon 5/2	Pick up folder path on stage is : \\192.168.31.18\mailroot / You can take Vinayak's help in accessing this folder.
	Tunnel 3 - Enroll Now	Review Steps 4-End	Step 4 is from OnBoard tunnel. Is this just placeholder? Will actual existing NH Enroll Now tunnel appear after OnBoard tunnel is completed?		Please advise		New hire enrollment tunnel will appear after onboard tunnel.

## Completed Req
PreBoard
Step #	Step Name	Change Summary	Change Detail	Status	Comments
1	Landing Page A Welcome to MATT	Title in Red		Done
		Left justify title		Done
		All CAP words in Red		Done
		People in Caps, Red		Done
		Revise 2nd line: Replace "We are a diverse…" with "Our goal…"		Done
		Remove Gap between pics and last sentence		Done
		Reduce photo size by 50%		Done
		Change name of page to Welcome to Matt		Done
		Photo Image improvement -Please display pictures in a single horizonal row across the page.		Done
2	Landing Page B Begin PreBoard	Title in Red		Done
		Change name of page to Begin PreBoard		Done
		Change all wording		Done
3	Demographics	Make Uneditable	EIN	Done
			Employee ID	Done
			Employee Type	Done
			Date of Employment	Done
			Receive Email	Done
			Most Recent Hire Date	Done
			Effective Date	Done
		Make Editable	Street Address 2	Done
			Title	Done
		Make Manditory	Legal First Name	Done
			Last Name	Done
			Preferred First Name	Done
			Social Security No	Done
			Gender	Done
			Date of Birth	Done
			Street Address	Done
			City	Done
			State	Done
			Postal Code	Done
			Home Phone	Done
			Email Address	Done
			Marital Status	Done
			Emergency Contact Name	Done
			Relationship	Done
			Emergency Telephone Number	Done
4	Questionaire	Change questions		Done
		Remove FB/Twitter/LI text		Done
5	I9	Pre-Populate	State, Name, DOB, SS, Address, Email, Telephone #	Done
		Notification of Rejected I9 should be sent to: Valerie Yost @ vyost@mattconstruction.com		Done
		Change Signature box to Employee Name field - still manditory		Done
		Correct inability to type first, last name without space to be accepted		Done
		Make Manditory	All fields above check boxes	Done
6	W4	Add State Form Link		Done
		Links should be (in this order) Federal W4 Form; CA Withholding Form; W4 Worksheet.		Done
		Make all 3 links larger/red - see note at bottom		Done
		Change Signature box to Employee Name field - still manditory		Done
		Add wording: To access forms or worksheet, please click on the links below. to end of text yellow box at top of page.Add wording: To access forms or worksheet, please click on the links below. to end of text yellow box at top of page.Add wording: To access forms or worksheet, please click on the links below. to end of text yellow box at top of page.		Done
		Add Federal, State W4s and associated worksheet to Home/My Profile for employee access/update at later date	Add to Home/OnBoard/ Quicklinks	Done
7	Notice to EE	Pre-Populate	All Wage Information and Paid Sick Leave fields. Pull from Payroll page in Ben Admin. If field does not exist in Payroll, please create and make manditory for ER.	Done
			Name	Done
			Left justify EMPLOYEE	Done
			Left justify EMPLOYER	Done
			Left justify PAID SICK LEAVE	Done
			Left justify WORKMAN'S COMPENSATION	Done
			Left justify WAGE INFORMATION	Done
			Fields to prepopulate with Demographic Info: Employee Name, Start Date. Change the following from editable field to uneditable text: Legal Name of Hiring Employer: MATT Construction, Is Hiring Employer a staffing agency…: NO; Physical Address of Hiring Employer's Main Office: 9814 Norwalk Blvd, Suite 100, Sante Fe Springs, CA 90670; Hiring Employer's Telephone Number: 562-903-2277; Worker's Compensation Section: Insurance Carrier's Name: Gallagher Basset Services, Inc.; Address: P.O. Box 23812 Tucson, AZ 85734; Telephone Number: 877-265-5186; Policy No: 71WC12376308	Done
			Reduce space between Paid Sick leave bullets and boxes below	Done
			Check Paid Sick leave bullet and check box alignment	Done
			4/8 - When viewing as test EE would not advance to next step after completing manditorty fields.	Done
			Change Signature box to Employee Name field - still manditory	Done
			Start Date - Pull from Date of Hire	Done
8	Direct Deposit	Remove "Memo" verbiage at top		Done
		Add Mail To info after 2nd paragraph		Done
		Add link to form. Attached to ticket		Done
		Move zip code to right of CA		Done
		Left Justified	All Headers
		Entire policy must show - See full document in Word format on ticket		Done
		Remove Signature Box		Done
		Name/Date fields marked manditory		Done
10	Drug Policy	Pre-Populate	Signature Date	Done
		Left justify title		Done
		Reformat to fit whole screen		Done
		Add Link	Add link to the document shown on the page so employee can print later	Done
		Remove pdf and show whole policy		Done
		Ensure there are 3 signature fields		Done
		Ensure that all signature fields manditory		Done
		Remove 3 Signature Boxes, Rename "Print Name" to Employee Name on each. Employee Name box to be manditory		Done
		Make list of classifications a bullet list		Done
		Correct inconsistent spacing between all sections/headers		Done
12	Cell Phone Order	Make 1st drop down manditory field		Done
		Revise whole page to include new verbiage		Done
13	Business Card Order	Add verbiage at top		Done
		Change Name wording		Done
		Make 1st drop down manditory field		Done
		Change LEED wording		Done
		Remove all other fields		Done
14	Benefit Overview	Add wording to botton 'Please take some time…"		Done
		Move new "Please take some time.." to position above links		Done
		Left justify Title		Done
		Ensure bullet points are aligned		Done
		Make links at botton larger, closer together			Can not be done
15	Ending Page A PreBoard Complete	Change name of page to PreBoard Complete		Done
		Title in Red		Done
OnBoard
1	On Board Overview	Unbold bullet points		Done
2	Intro to MATT Culture	Left justify Title		Done
		Title Red		Done
		Unbold bullet text		Done
		Question "What are the Unique…": left justify, blue font, double size		Done
3	Culture Video	Add wording at top of page: Title: Video Introduction to Matt Culture. Under title: Please allow some time for the video to load.		Done
		Video not showing, no link, no window			Client will check again
		Text	The text on this page needs to be anchored to the page. Currently populating at sametime video loads which negates the use of the verbiage.	Done
5	Building Your Career	Title Red		Done
		Unbold bullet text		Done
		Add "s" to the word questions in 4th bullet		Done
6	What to Expect	Title Red		Done
		Reduce graph size to 75 or 80%		Done
		Replace graphic with the new (more horizonatal) version attached to ticket.		Done
		Reduce space between graph and last line		Done
7	30-60-90	Title Red		Done
		Reduce graph size to 75 or 80%		Done
8	Our Performance	Title Red		Done
		Title Left justified		Done
		Fix typo "it's" and remove extra space before colon - perhaps make the line left justified instead of full justified?		Done
		Final sentence of 1st paragraph fix to "life-long"		Done
		3rd paragraph title fix "Bi-Annually" and add dash after "two times each year"		Done
		5th paragraph add semicolon after December		Done
9	Training & Dev	Graphic	Please move graphic more to right and make 50% larger	Done	increase the Image to 50% however it cannot be move further to right
		Title Red		Done
		Add wording to Internal Training paragrah		Done
		Remove white space before External Training paragraph		Done
		Make 70+20+10 graphic small and to the right side of Internal Training paragraph - use Word Wrap to achieve?		Done	increase the Image to 50% however it cannot be move further to right
10	Materials & Resources	Title Red		Done
		Revise 4th bullet wording		Done
		5 Bullet point are to be links and RED		Done	Can not be done
		Change 2nd line to "Materials and resources related to your career and development are available in the links below:"		Done
11	Ending page B OnBoard Complete	Title Red		Done
		Title Left justified		Done
		All Text Left Justified		Done
		Change name of page to OnBoard Complete		Done
		Blue font on last sentence		Done
12	Ending Page C Begin Benfit Enrollment	Change the name of this page on Steps to Begin Benefit Enrollment		Done
		Add this page		Done
General
Various	Various	Add links to all documents found on OnBoard Step 10 Materials & Resources to benAdmin/My Profile/Additional Forms		Done
		Implement Notification of Completion @ 1) Each Stage, 2)Makes Change to W4, 3)Approval of changes - Notification to go via email to vyost@mattconstruction.com		Done
		Ensure all links are red and the same size as the ones at the bottom of PreBoard Step 14 Benefit Overview		Done
		Once EE has completed tunnels, where does ER go to view all information and forms? Need to create a tutorial for ER before launch.		Done
		All Signature Fields are Manditory	Correct Preboard 7	Done
		Links to be same Size and color red as on Preboard Step 4 (W4)	Correct Preboard 8, 14	Done	Unable to remove as it is necessary for ACA function.
		User Name	Need to make Date of Birth and SS# non-manditory in Ben Admin so a user name can be generated after Add EE. ER unable to access this info before EE completes tunnel.	Done
		Dummy Password	Need to create a dummy password to be used with WT generated Username since DOB/SS# will not be assessable to ER at time of Add EE	Done
		ER Access	Where will ER be able to download forms after complete by EE? (PreBoard 4, 5, 6, 7, 9, 10, 11, 12, 13)	Done
	BenAdmin Add Emp	Non-Manditory	Date of Birth field	Done
	BenAdmin Demographics	Pre-Populate	Pre-populate BenAmin Demographics page Employee ID with 1st 3 letters of first name, 1st 3 letters of last name, last 2 digits of SS# - After New Hire completes the tunnel	Done

## Add NH Procedure
Procedure for Adding New Hire Info

Ben Admin
	Add Employee
		First Name
		Last Name
		Gender
		Email
		Date of Employement
		Salary
		Job Title
		Payroll Schedule
Ben Admin
	Payroll
		OT Rate Multiplier
		Paid Sick Leave (# of PTO?)
		Sick Leave Check Box