## Unfinished Req
Step # | Step Name | Change Summary | Change Detail | Status | WT Comments 5/19 | Est Date of Complete | Harbinger Comments 05/19 | Harbinger Comments 05/24 | Harbinger Comments 05/26 | Harbinger Comments 05/30 |  |  |  | Harbinger ComHarbinger Comments 05/26ments 05/26
PreBoard
3 | Demographics | Add Text | Add following text at top of page, under current text. (Maintain font size and bold text): Please pay particular attention to correcting your Date of Birth. Please create your Employee ID by entering the 1st 3 letters of your first name, the 1st 3 letters of your last name and the last 2 digits of your Social Security number. EX - Jane Doe 547-89-3698 would be jandoe98.Add following text at top of page, under current text. (Maintain font size and bold text): Please pay particular attention to correcting your Date of Birth. Please create your Employee ID by entering the 1st 3 letters of your first name, the 1st 3 letters of your last name and the last 2 digits of your Social Security number. EX - Jane Doe 547-89-3698 would be jandoe98.Add following text at top of page, under current text. (Maintain font size and bold text): Please pay particular attention to correcting your Date of Birth. Please create your Employee ID by entering the 1st 3 letters of your first name, the 1st 3 letters of your last name and the last 2 digits of your Social Security number. EX - Jane Doe 547-89-3698 would be jandoe98. | 05-30-2016 This is done as enhancement and verified on stage. | See Email to Amit dated 5/20/16 | 2016-05-20 | This is kept ON-HOLD for today,because we got an approval for WT-2141- Pre-populate BenAdmin Demographics page and this is deployed on our local environment and is in QA phase. Do let us know would you still like to go with adding text ? If Yes, End Date will be 05/20.This is kept ON-HOLD for today,because we got an approval for WT-2141- Pre-populate BenAdmin Demographics page and this is deployed on our local environment and is in QA phase. Do let us know would you still like to go with adding text ? If Yes, End Date will be 05/20.This is kept ON-HOLD for today,because we got an approval for WT-2141- Pre-populate BenAdmin Demographics page and this is deployed on our local environment and is in QA phase. Do let us know would you still like to go with adding text ? If Yes, End Date will be 05/20. |  | Completed |  | Text in module is incorrect. Says below. Please take the time to complete your demographic information accurately, as this is the basis of your employee record. (Maintain font size and bold text): Please pay particular attention to correcting your Date of Birth and Social Security Number. remove the red above and change wording to that in column N | Should say: Please take the time to complete your demographic information accurately, as this is the basis of your employee record. Please pay particular attention to correcting your Date of Birth.
|  | Make Manditory and Editable | EmployeeID | 05-30-2016 Done. EmployeeID is mandatory now on this page. | [7 empty] | Employee should be able to edit their employee ID as requested by the Employer in above statement at top of screen. Right now it is non editable on the employee page | Was this requested to be mandatory on Employer side? Don't show required job title, employee type, etc.
|  | Make Non Mandatory | Preferred Name | 05-30-2016 : done |  |  |  |  | Done |  | X
5 | I9 | Allow Two Words | Need to allow two separate words (Same as Employee Name/Signature field) | 05-30-2016 This is done as enhancement and verified on stage. | Sorry that I was unclear. This is for the OTHER NAMES USED field | [5 empty] | X
|  | Process Clarification on Guide | How does the form get submitted to eVerify after Admin completes Section 2? | We were analyzing this at our end and also communicating with Everify for same. We'll be sharing you a document shortly
|  | Make Mandatory/RED | Address, City, State, Zipcode, email address, telephone # | Please refer WT-1918;We've implemented this as per Diana's comments | [6 empty] | This is not red on the I9 however was red on ee demographic page and auto filled into I9.
|  | Date box | Remove calendar pop-up. Make field uneditable | 05-30-2016 This is done as enhancement and verified on stage. |  | 2016-05-25 |  | 2016-05-27 | Stage deployment: 27 May |  | X
6 | W4 | Date box | Remove calendar pop-up. Make field uneditable | 05-30-2016 This is done as enhancement on LB. |  | 2016-05-26 |  | 2016-05-28 | Stage deployment: 27 May |  | X
|  | Add 's' to end of word differ (Near checkbox)Add 's' to end of word differ (Near checkbox)Add 's' to end of word differ (Near checkbox) |  | Done; In QA on Harb. Environment |  |  |  | 2016-05-28 | Stage deployment: 27 May
|  | Make Manditory | Total # of Withholdings | 05-30-2016 : This is done as enhancement on LB. . |  | 2016-05-26 |  | 2016-05-28 | Stage deployment: 27 May |  | X
10 | Drug Policy | Signature Field | Rename field to Employee Name | 05-30-2016 Done. |  |  |  | Earlier Field name was Name , Now changed to Employee Name |  |  | X
13/14 | Benefit Overview/Bus Card Order | Step Order Change? | Move Bus Card Order Step back to location previous to Benefit Overview…why changed? | 05-30-2016 Existing order is as given. |  |  |  | Done, kindly check
OnBoard
|  | No OnBoard tunnel available - See message |  | NA; This is available;kindly check Amit's comments in WT-610
Enrollment
|  | No Enrollment tunnel available |  | NA; This is available;kindly check Amit's comments in WT-610
Misc
Ben Admin | Add EE | Make Manditory | Job Title | 05-30-2016 Done. | Job Title (drop down with EE, Executive, Owner) in BenAdmin/Add EE is already manditory, but needs to be colored RED. Admin must complete this field in order to complete the manditory Payroll Schedule field. EE does not use this field. Needs to be red and seen correctly from PA view also.Job Title (drop down with EE, Executive, Owner) in BenAdmin/Add EE is already manditory, but needs to be colored RED. Admin must complete this field in order to complete the manditory Payroll Schedule field. EE does not use this field. Needs to be red and seen correctly from PA view also. |  |  | As of now changes available is only for CA and EE login, partner will not see that. Kindly create a test admin and verify As of now changes available is only for CA and EE login, partner will not see that. Kindly create a test admin and verify
| Payroll | Make Mandatory/RED | Paid Sick leave | Incomplete 05-30-2016 Done. |  |  |  | Done
|  | Make Mandatory/RED | (2) Written Agreement…Drop Downs | Incomplete 05-30-2016 Done. |  |  |  | Done
|  | Make Mandatory/RED | Overtime Multiplier | Incomplete 05-30-2016 Done. |  |  |  | Done
|  | Pre-Populate | Can the CURRENT RATE populate with salary just as with GROSS ANNUAL SALARY from Add EE screen? | Incomplete 05-30-2016: This is not possible since Payroll is a Static/Base page wherein Map field component do not come; |  |  |  | Presently this is not possible since Payroll is a Static/Base page wherein Map field component do not come
| N/A | Forms Available for Access to Admin | The following changes need to be made to Ben Admin/EE/Additional Forms: ADD-W4, Cell Phone Order; REMOVE-Welcome to MATT, Direct Deposit, Benefit Overview, OnBoard Overview, Intro to MATT, Building Your Career, Performance, Materials & Resources.The following changes need to be made to Ben Admin/EE/Additional Forms: ADD-W4, Cell Phone Order; REMOVE-Welcome to MATT, Direct Deposit, Benefit Overview, OnBoard Overview, Intro to MATT, Building Your Career, Performance, Materials & Resources. | Incomplete 05-30-2016 Done except for W4. It is visible from EE additional form |  |  |  | Done
| N/A | Need Guide | Admin process to add EE (BenAdmin Add EE/BenAdmin Payroll | Please elborate more on this ?
| I9 Section 2 - Admin | Remove Line? | Remove Employee Last name, First name and Middle Initial/Name from Section 1 line at top of Section 2?Remove Employee Last name, First name and Middle Initial/Name from Section 1 line at top of Section 2? | Incomplete |  |  | WT-2575 - Waiting for Dave's approval |  | Stage deployment date : 1 June
|  | Make Mandatory/RED | List B - Document Number, Expiration Date | Incomplete
|  | Make Mandatory/RED | List C - Issuing Authority, Document Number | Incomplete
|  | Pre-Populate - Incorrect | Certification Section: EE First Date of Emp should populate with DOH, not current date | Incomplete
|  |  | List B & C Expiration Date should not populate with current date | Incomplete
|  | Make Non Mandatory | List C Expiration Date | Incomplete
|  | Allow Two Words | Certification Section: Name of ER Auth Rep field needs to allow two words | Incomplete
|  |  | Certification Section: Title of Auth Rep field needs to allow two words | Incomplete
|  | Remove duplicate fields | Certification Section: Last Name field, First Name field are redundant of ER or Auth Rep field. | Incomplete
|  | Populate, uneditable | ER Business or Org: MATT Construction | Incomplete
|  |  | Address: 9814 Norwalk Blvd., Suite 100 | Incomplete
|  |  | City: Santa Fe Springs | Incomplete
|  |  | State: CA | Incomplete
|  |  | Zip Code: 90670 | Incomplete
NOTE: IF AT ALL POSSIBLE, PLEASE MAKE ALL VIEWS THE SAME FOR CLIENT ADMIN AND WT ADMIN. IT IS DIFFICULT TO CO-TEST IF WE ARE SEEING DIFFERENT VALUES SUCH AS WHICH FIELDS ARE RED/MANDATORY. THANKS.
Harb reply: | Admin rights remains the same no matter it is WT admin or Client admin , both are in company admin roles

## Completed Req
PreBoard
Step # | Step Name | Change Summary | Change Detail | Status | Comments
1 | Landing Page A Welcome to MATT | Title in Red |  | Done
|  | Left justify title |  | Done
|  | All CAP words in Red |  | Done
|  | People in Caps, Red |  | Done
|  | Revise 2nd line: Replace "We are a diverse…" with "Our goal…" |  | Done
|  | Remove Gap between pics and last sentence |  | Done
|  | Reduce photo size by 50% |  | Done
|  | Change name of page to Welcome to Matt |  | Done
|  | Photo Image improvement -Please display pictures in a single horizonal row across the page. |  | Done
2 | Landing Page B Begin PreBoard | Title in Red |  | Done
|  | Change name of page to Begin PreBoard |  | Done
|  | Change all wording |  | Done
3 | Demographics | Add verbiage at top | Please take the time to complete your demographic information accurately, as this is the basis of your employee record. | Done
|  | Make Uneditable | EIN | Done
|  |  | Employee ID | Done
|  |  | Employee Type | Done
|  |  | Date of Employment | Done
|  |  | Receive Email | Done
|  |  | Most Recent Hire Date | Done
|  |  | Effective Date | Done
|  | Make Editable | Street Address 2 | Done
|  |  | Title | Done
|  | Make Manditory | Legal First Name | Done
|  |  | Last Name | Done
|  |  | Preferred First Name | Done
|  |  | Social Security No | Done
|  |  | Gender | Done
|  |  | Date of Birth | Done
|  |  | Street Address | Done
|  |  | City | Done
|  |  | State | Done
|  |  | Postal Code | Done
|  |  | Home Phone | Done
|  |  | Email Address | Done
|  |  | Marital Status | Done
|  |  | Emergency Contact Name | Done
|  |  | Relationship | Done
|  |  | Emergency Telephone Number | Done
4 | Questionaire | Change questions |  | Done
|  | Remove FB/Twitter/LI text |  | Done
5 | I9 | Pre-Populate | State, Name, DOB, SS, Address, Email, Telephone # | Done
|  | Notification of Rejected I9 should be sent to: Valerie Yost @ vyost@mattconstruction.com |  | Done
|  | Change Signature box to Employee Name field - still manditory |  | Done
|  | Correct inability to type first, last name without space to be accepted |  | Done
6 | W4 | Add State Form Link |  | Done
|  | Links should be (in this order) Federal W4 Form; CA Withholding Form; W4 Worksheet. |  | Done
|  | Make all 3 links larger/red - see note at bottom |  | Done
|  | Change Signature box to Employee Name field - still manditory |  | Done
|  | Add wording: To access forms or worksheet, please click on the links below. to end of text yellow box at top of page.Add wording: To access forms or worksheet, please click on the links below. to end of text yellow box at top of page.Add wording: To access forms or worksheet, please click on the links below. to end of text yellow box at top of page. |  | Done
|  | Add Federal, State W4s and associated worksheet to Home/My Profile for employee access/update at later date | Add to Home/OnBoard/ Quicklinks | Done
7 | Notice to EE | Pre-Populate | All Wage Information and Paid Sick Leave fields. Pull from Payroll page in Ben Admin. If field does not exist in Payroll, please create and make manditory for ER. | Done
|  |  | Name | Done
|  |  | Left justify EMPLOYEE | Done
|  |  | Left justify EMPLOYER | Done
|  |  | Left justify PAID SICK LEAVE | Done
|  |  | Left justify WORKMAN'S COMPENSATION | Done
|  |  | Left justify WAGE INFORMATION | Done
|  |  | Fields to prepopulate with Demographic Info: Employee Name, Start Date. Change the following from editable field to uneditable text: Legal Name of Hiring Employer: MATT Construction, Is Hiring Employer a staffing agency…: NO; Physical Address of Hiring Employer's Main Office: 9814 Norwalk Blvd, Suite 100, Sante Fe Springs, CA 90670; Hiring Employer's Telephone Number: 562-903-2277; Worker's Compensation Section: Insurance Carrier's Name: Gallagher Basset Services, Inc.; Address: P.O. Box 23812 Tucson, AZ 85734; Telephone Number: 877-265-5186; Policy No: 71WC12376308 | Done
|  |  | Reduce space between Paid Sick leave bullets and boxes below | Done
|  |  | Check Paid Sick leave bullet and check box alignment | Done
|  |  | 4/8 - When viewing as test EE would not advance to next step after completing manditorty fields. | Done
|  |  | Change Signature box to Employee Name field - still manditory | Done
|  |  | EE/ER dates boxes populate with current date | Done
|  |  | Start Date - Pull from Date of Hire | Done
8 | Direct Deposit | Remove "Memo" verbiage at top |  | Done
|  | Add Mail To info after 2nd paragraph |  | Done
|  | Add link to form. Attached to ticket |  | Done
|  | Move zip code to right of CA |  | Done
9 | Safety Orientation | Left Justified | All Headers
|  | Entire policy must show - See full document in Word format on ticket |  | Done
|  | Pre-Populate | Signature Date, remove calendar pop-up, make uneditable | Done
|  | Change Signature box to "Employee Name" field |  | Done
|  | Remove Signature Box |  | Done
|  | Name/Date fields marked manditory |  | Done
10 | Drug Policy | Pre-Populate | Signature Date | Done
|  | Left justify title |  | Done
|  | Reformat to fit whole screen |  | Done
|  | Add Link | Add link to the document shown on the page so employee can print later | Done
11 | Mobile Device Policy | Remove pdf and show whole policy |  | Done
|  | Ensure there are 3 signature fields |  | Done
|  | Ensure that all signature fields manditory |  | Done
|  | Remove 3 Signature Boxes, Rename "Print Name" to Employee Name on each. Employee Name box to be manditory |  | Done
|  | Make list of classifications a bullet list |  | Done
|  | Pre-Populate | Signature Date (3), remove calendar pop-up, make uneditable | Done
|  | Correct inconsistent spacing between all sections/headers |  | Done
12 | Cell Phone Order | Make 1st drop down manditory field |  | Done
|  | Revise whole page to include new verbiage |  | Done
13 | Business Card Order | Add verbiage at top |  | Done
|  | Change Name wording |  | Done
|  | Make 1st drop down manditory field |  | Done
|  | Change LEED wording |  | Done
|  | Remove all other fields |  | Done
14 | Benefit Overview | Add wording to botton 'Please take some time…" |  | Done
|  | Move new "Please take some time.." to position above links |  | Done
|  | Left justify Title |  | Done
|  | Ensure bullet points are aligned |  | Done
|  | Make links at botton larger, closer together |  |  | Can not be done
15 | Ending Page A PreBoard Complete | Change name of page to PreBoard Complete |  | Done
|  | Title in Red |  | Done
OnBoard
1 | On Board Overview | Unbold bullet points |  | Done
2 | Intro to MATT Culture | Left justify Title |  | Done
|  | Title Red |  | Done
|  | Unbold bullet text |  | Done
|  | Question "What are the Unique…": left justify, blue font, double size |  | Done
3 | Culture Video | Add wording at top of page: Title: Video Introduction to Matt Culture. Under title: Please allow some time for the video to load. |  | Done
|  | Video not showing, no link, no window |  |  | Client will check again
|  | Text | The text on this page needs to be anchored to the page. Currently populating at sametime video loads which negates the use of the verbiage. | Done
5 | Building Your Career | Title Red |  | Done
|  | Unbold bullet text |  | Done
|  | Add "s" to the word questions in 4th bullet |  | Done
6 | What to Expect | Title Red |  | Done
|  | Reduce graph size to 75 or 80% |  | Done
|  | Replace graphic with the new (more horizonatal) version attached to ticket. |  | Done
|  | Reduce space between graph and last line |  | Done
7 | 30-60-90 | Title Red |  | Done
|  | Reduce graph size to 75 or 80% |  | Done
| Notice to EE | Make Changes | See Step 7 Change Notes 05.13.16 attached to WT-610 | Done
8 | Our Performance | Title Red |  | Done
|  | Title Left justified |  | Done
|  | Fix typo "it's" and remove extra space before colon - perhaps make the line left justified instead of full justified? |  | Done
|  | Final sentence of 1st paragraph fix to "life-long" |  | Done
|  | 3rd paragraph title fix "Bi-Annually" and add dash after "two times each year" |  | Done
|  | 5th paragraph add semicolon after December |  | Done
9 | Training & Dev | Graphic | Please move graphic more to right and make 50% larger | Done | increase the Image to 50% however it cannot be move further to right
|  | Title Red |  | Done
|  | Add wording to Internal Training paragrah |  | Done
|  | Remove white space before External Training paragraph |  | Done
|  | Make 70+20+10 graphic small and to the right side of Internal Training paragraph - use Word Wrap to achieve? |  | Done | increase the Image to 50% however it cannot be move further to right
10 | Materials & Resources | Title Red |  | Done
|  | Revise 4th bullet wording |  | Done
|  | 5 Bullet point are to be links and RED |  | Done | Can not be done
|  | Change 2nd line to "Materials and resources related to your career and development are available in the links below:" |  | Done
11 | Ending page B OnBoard Complete | Title Red |  | Done
|  | Title Left justified |  | Done
|  | All Text Left Justified |  | Done
|  | Change name of page to OnBoard Complete |  | Done
|  | Blue font on last sentence |  | Done
12 | Ending Page C Begin Benfit Enrollment | Change the name of this page on Steps to Begin Benefit Enrollment |  | Done
|  | Add this page |  | Done
General
Various | Various | Add links to all documents found on OnBoard Step 10 Materials & Resources to benAdmin/My Profile/Additional Forms |  | Done
|  | Implement Notification of Completion @ 1) Each Stage, 2)Makes Change to W4, 3)Approval of changes - Notification to go via email to vyost@mattconstruction.com |  | Done
|  | Ensure all links are red and the same size as the ones at the bottom of PreBoard Step 14 Benefit Overview |  | Done
|  | Once EE has completed tunnels, where does ER go to view all information and forms? Need to create a tutorial for ER before launch. |  | Done
|  | All Signature Fields are Manditory | Correct Preboard 7 | Done
|  | Links to be same Size and color red as on Preboard Step 4 (W4) | Correct Preboard 8, 14 | Done | Unable to remove as it is necessary for ACA function.
|  | User Name | Need to make Date of Birth and SS# non-manditory in Ben Admin so a user name can be generated after Add EE. ER unable to access this info before EE completes tunnel. | Done
|  | Dummy Password | Need to create a dummy password to be used with WT generated Username since DOB/SS# will not be assessable to ER at time of Add EE | Done
|  | ER Access | Where will ER be able to download forms after complete by EE? (PreBoard 4, 5, 6, 7, 9, 10, 11, 12, 13) | Done
| BenAdmin Add Emp | Non-Manditory | Date of Birth field | Done
| BenAdmin Payroll | Add Fields (See PreBoard Step 7 "Notice to EE" Wage Info Section for reference | Rate By (Check Boxes) | Done
|  |  | Written Agreement…(verbiage) Yes/No Drop Down | Done
|  |  | If Yes…(verbiage) Yes/No Drop Down | Done
|  |  | Allowances if any…(Text Box) | Done
| BenAdmin EE Admin | Move | (WT-2141) Move I9 eVerify Password Reset from EE Administration to Security | Unable to fulfill
|  | Move | (WT-2143) Move I9 Approval Status from EE Administration to Review Changes | Unable to fulfill
|  | Move | (WT-2144) Move Supervisor Approval from EE Administration to Review Changes | Unable to fulfill
|  | Make Non-Manditory | Date of Birth, EE ID # | Unable to fulfill | False DOB will need to be entered. 1st 3 of First Name, 1st 3 of Last Name will be entered. Last two of SS# will need to be entered on Demographic Page by EE.
| BenAdmin Demographics | Pre-Populate | Pre-populate BenAmin Demographics page Employee ID with 1st 3 letters of first name, 1st 3 letters of last name, last 2 digits of SS# - After New Hire completes the tunnel | Unable to fulfill
| Tunnel 3 - Enroll Now | Review Steps 4-End | Step 4 is from OnBoard tunnel. Is this just placeholder? Will actual existing NH Enroll Now tunnel appear after OnBoard tunnel is completed? | Done
| N/A | Admin Notification | (WT-1788) Notification of ER (vyost@mattconstruction.com) when each tour is complete or when forms are changed by EE | Done | Per Vinayak - Once module is moved to Production, email notification will happen.
|  | Need Guide | For Admin to retreive completed forms after tunnel is complete | Done
| N/A | Need Guide | for EE to access forms to make changes in future | Done

## AdminNHAdd
Procedure for Adding New Hire Info
Ben Admin
Add Employee
First Name
Last Name
Date of Birth (false date)
Gender
Employee ID (xxxxxxxx)
Email
Date of Employment
Salary
Job Title
Payroll Schedule
Save
Obtain Username & Password for NH tunnel
BenAdmin Company Home
Search NH Name
Employee
Payroll
Section 1
Current Rate
Overtime Rate Multiplier (1, 1.5, etc)
Section 2
Paid Sick Leave (# of days)
Sick Leave Check Boxes
Rate By
Rate of Pay Written Agreement (2)
Allowances
Save

## EEChangeDocs
If EE wishes to makes changes to W4, etc., EE will access forms here:
(from EE login)
WT desktop

## AdminI9FormSubmit
Admin will access, complete and submit EE I9 form here:
OnBoard
EE Admin
I9 Form
Section 1 - Previously completed by EE
Section 2 - To be completed by Admin
Click Save
How does this get sent to eVerify now?