## Summary - Production move EHMC
Prime breakout plan for standalone "Encino Hospital Medical Center" | Company Details
Company Name : EHMC | Master / Legacy Company Name | Prime Healthcare
Move Date: 09th July 2016 | Company Name | EHMC
Black Out Start Date Time: Friday' 08th July 2016 07:30 PM PST | DB Name | Prime_Encino_Hospital_Medical_Center_12381
Black Out End Date Time: Saturday' 09th July 2016 06:00 AM PST | New Company ID | 12381
Contingency Plan
In case this split activity results in any issue, Back up of "Prime Healthcare" taken on start of blackout will be restored and company will be live without any change of data / customization.
Assumptions / Additional points discussed
"Prime Healthcare" will not be available during the mentioned blackout period
All midnight services will be executed only after breakout for EHMC is complete
Scheduled feeds for "Prime Healthcare" will be executed after completion of this activity
From Prime legacy company i.e "Prime Healthcare" we are only deactivating employee/company admin access for EHMC as of now until we receive a go ahead from cleint to remove this separated out class & related data entirely from legacy company
Respective AE will take care of assigning Company Admin rights / creating new CA login if required.
All EDI people, client will be notified by AE not to import / acess anything related to separated out class from Prime legacy company as it will still be acessible to Partner / Broker & SA roles. [ Until it is removed after approval ]
Access policy for Partners - No need to create any new partner this time

## Classes
Class2ID
15,19,42,6,5,41,4,11
Class 1 / Facility |  | Class 2 / Classification
ID | Name | ID | Name
19 | Encino Hospital Medical Center | 4 | Full Time Employees
|  | 5 | Part Time Employees
|  | 6 | Per Diems
|  | 11 | Physicians
|  | 15 | CFOFT CNA
|  | 19 | Csuite
|  | 41 | SEIU 121 Full Time
|  | 42 | SEIU 121 Part Time

## Feeds
Template to be removed
Templates moved to global level
List of all feeds on Prime with Class , Grouping & Schedule details - Encino Hospital Medical Center
Status | Template ID | Template Name | Group Template Name | Last Export Date | Schedule Type | Schedule Day | Global Level Schedule | Interval Period | Start Date Time | Class1 IDs | Class2 IDs
Scheduled | 10 | Prime Healthcare Services_Keenan_Eldorado 834 5010 | Prime Healthcare Services_Keenan_Eldorado 834 5010_Group | 2016-07-04 09:01 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,13,44,14,15,42,40,41,51,36,37,52,16,43,27,28,7,38,57,60,35,34,17,29,30,20,21,58,53
Scheduled | 180 | MediTech CS Encino Hospital Medical Center | _Prime MediTech CS Encino Hospital Medical Center | 2016-07-04 05:56 |  |  | Daily with Interval | 0 |  | 19
Scheduled | 495 | Global Search Member | Prime Global Search Member | 2016-06-30 15:31 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,7,48,38,57,60,35,34,17,29,30,20,21,58,53
Scheduled | 387 | NEW HR Simplified COBRA Participant | Prime Healthcare_NEW HR Simplified COBRA Participant_Group | 2016-06-30 15:21 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,32,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 386 | NEW HR Simplified COBRA DEPENDENT | Prime Healthcare_NEW HR Simplified COBRA DEPENDENT_Group | 2016-06-30 15:11 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,32,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 385 | NEW HRSimplified_COBRA Coverage | Prime Healthcare_NEW HRSimplified_COBRA Coverage_Group | 2016-06-30 15:01 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,32,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 26 | Hyatt Legal | Prime Healthcare_Hyatt Legal_Group | 2016-06-30 10:04 |  |  | Weekly | 0 |  | 0,26,8,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,60,35,34,17,29,30,20,21,58,53
Scheduled | 24 | DeltaCare HMO 834 5010 | Prime Healthcare_DeltaCare HMO 834 5010_Group | 2016-06-30 08:21 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,46,49,22,47,45,13,44,14,15,42,40,41,51,36,37,52,16,43,27,28,56,7,31,33,48,55,38,57,32,35,34,17,29,30,20,21,53,50
Scheduled | 12 | Delta Dental PPO 834 5010 | Prime Healthcare Delta Dental PPO 834 5010_Group | 2016-06-30 07:31 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,38,57,35,34,17,29,30,20,21,58,53
Scheduled | 486 | Davis Vision Eligibility_Subscriber | Prime Healthcare_Davis Vision | 2016-06-30 07:08 |  |  | Weekly | 0 |  | 0,26,8,9,10,0,54,11,12,19,46,49,22,47,45,13,44,14,15,23,42,40,41,24,51,59,36,37,52,16,61,43,27,28,56,7,31,33,48,55,38,57,32,60,35,34,17,29,30,20,21,58,53,50,25
Scheduled | 487 | Davis Vision Eligibility_Dependents | Prime Healthcare_Davis Vision | 2016-06-30 07:08 |  |  | Weekly | 0 |  | 0,26,8,9,10,0,54,11,12,19,46,49,22,47,45,13,44,14,15,23,42,40,41,24,51,59,36,37,52,16,61,43,27,28,56,7,31,33,48,55,38,57,32,60,35,34,17,29,30,20,21,58,53,50,25
Scheduled | 17 | Prime Healthcare Services VSP_834 5010 | Prime Healthcare Services VSP_834 5010_Group | 2016-06-30 06:11 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,38,57,35,34,17,29,30,20,21,53
Scheduled | 23 | Aetna Lower Bucks 834 5010 | Prime Healthcare_Aetna Lower Bucks 834 5010_Group | 2016-06-30 06:06 |  |  | Weekly | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
Scheduled | 31 | MetLife_Dental_5010 834_Prime Healthcare Services | Prime Healthcare _MetLife_Dental_5010 834_Group | 2016-06-29 09:43 |  |  | Weekly | 0 |  | 0,19,22,47
Scheduled | 2 | Prime Healthcare Services HR Simplified FSA and DCA feed | Prime Healthcare Services HR Simplified FSA and DCA feed | 2016-06-29 06:03 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,46,49,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,33,38,57,60,35,34,17,29,30,20,21,58,53,50
| 510 | HR Simplified FULL FSA |  | 2016-06-29 03:19 |  |  |  | 0 |  | 0,26,8,9,10,11,12,19,46,49,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,33,38,57,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 221 | Sun Life EOI_EHMC | Prime_SunLife_EOI_Group | 2016-06-24 07:00 |  |  | Weekly | 0 |  | 19
| 426 | EDI Audit VSP | Prime Healthcare_EDI Audit VSP_Group | 2016-05-09 10:17 |  |  |  | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,7,48,38,57,60,35,34,17,29,30,20,21,58,53
| 423 | EDI Audit Delta Dental PPO | Prime Healthcare_EDI Audit Delta Dental PPO_Group | 2016-05-09 09:24 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 21 | HR Simplified_COBRA_Coverage |  | 2016-03-24 05:34 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57
| 422 | _EBS AddChangeTerm |  | 2016-03-08 17:45 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 472 | EDI Audit Aetna |  | 2016-01-06 21:54 |  |  |  | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,7,48,38,57,60,35,34,17,29,30,20,21,58,53
| 432 | Test |  | 2015-12-23 02:07 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 424 | EDI Audit DeltaCare HMO | Prime Healthcare_EDI Audit DeltaCare HMO_Group | 2015-12-07 18:03 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 20 | HRSimplified_COBRA_Dependent |  | 2015-08-06 07:34 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56
| 19 | HR Simplified_COBRA_Participant |  | 2015-08-06 07:24 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56
| 200 | zDependent Audit Data Demographic Census (do not use) |  | 2014-12-23 15:50 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 60 | Enrollment Counts | Prime_Enrollment Counts_Group | 2014-10-12 18:18 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 41 | Lawson | Lawson_Group |  |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 85 | LHP Payroll Supp Life | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 86 | LHP Payroll File Voluntary Life | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 382 | Equifax Employee Benefits Worksheet | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 383 | Equifax Dependent Benefit Worksheet | Prime_Equifax Dependent Benefit Worksheet_Group |  |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 384 | Equifax Employee Benefit Worksheet Waives | Prime_Equifax Employee Benefit Worksheet Waives_Group |  |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 421 | Prime Health HNAS 834 5010 | [5 empty] | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,56,7,48,55,38,57,60,35,34,17,29,30,20,21,58,53
| 425 | _EBS COBRA Terms weekly | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 436 | Test_Clone | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 442 | EBS Newly Enrolled COBRA | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 452 | MediTech CS Encino Hospital Medical Center_Life | [5 empty] | 0 |  | 19
| 480 | test prime imputed amount | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61

## Split steps Master Plan
Milestones marked in yellow color
Task Description | Owner | Cut off time | Status
Pre-requisites
Check list of Class1 & Class2 values to keep on new company | Saurabh | 2 days prior
Check list of Class2 values to keep on Main Prime company | Saurabh | 2 days prior
Intimate for Black out date & time to all stakeholders | Saurabh | 2 days prior
Check all scheduled feeds for New group company & Prime Healthcare | Saurabh | 2 days prior
Create Group level templates for new group - 1 day in advance | Hrishikesh | 2 days prior
Network support engineer availability check & Team availability check | Samir / Satya / Sachin | 1 week prior
Keep scripts compiled and ready for Production | Ashwin | 1 days prior
Add config changes for Import Export config on production for new company tag | Rohan | 2 days prior
Save Class1 & Class2 values on Export templates for Prime Healthcare where ever criteria is null / none | Saurabh | 2 days prior
Server activities
Stop Import Export Scheduler service | Ashwin | 9:00
Inactive Prime Healthcare - main company | Ashwin | 9:00
Delete CDC for Prime Healthcare main company | Indra | 9:00
Start Import Export Scheduler service for other company feeds to pick up | Ashwin | 9:00
Take backup of Prime Healthcare & Online Enrollment and keep in DO NOT Delete | Indra | 9:00
Attach this back up manually with Name "EHMC" on Production | Indra | 9:00
Add entry in OnlineEnrollment > Company table, keep company inactive | Ashwin | 10:00
Copy assets and files on web / file server with new company ID Generated Files (sequence-bar etc), Images,Stylesheet and Forms(File Server) | Ashwin | 10:00
ON CLUSTER Only Need to Give rights to SA user for this company to Dashboard [Default Rights to Dashboard while company migrating from stage to production.sql] | Ashwin | 10:00
Execute company split scripts and steps | Saurabh
Activate this new Company on production | Saurabh | 11:30
Generate all eligibility criteria using Workterra Utility | Saurabh | 11:30
Save EDS pages, selection Module on Module mapping screen, save theme | Saurabh | 11:30
Save Theme from Site branding & theme (Theme for Prime Healthcare) | Saurabh | 11:30
Save Dashboard configuration for Employees, Partner, Company Admin | Saurabh | 11:30
Upload logo for EHMC company | Saurabh | 11:30
Remove Classwise images for other classes | Saurabh | 11:30
Create user access policy for new partners | Saurabh | 11:30
Move PGP Keys to Global level | Saurabh | 11:30
Add company ID in service configuration file- Workterra service scheduler | Ashwin | 11:30
Open company for QA Testing | Saurabh | 11:45
Execute Workterra scheduler service for new company | Ashwin | 12:00
Initial approval from QA for no breaking points | Hrishikesh | 13:00
Deactivate respective class from Prime Healthcare main company on production | Saurabh
Handover Prime Healthcare main company to QA for testing except reports | Saurabh | 14:00
Feeds creation and scheduling | Hrishikesh | 14:30
Verify export feed schedules | Rohan | 14:30
Enable CDC on New company | Indra | 16:00
Enable CDC for Prime Healthcare | Indra | 16:00
Verify reports after replication is up | Hrishikesh | 17:30
QA Approval for entire process | Hrishikesh | 17:30
Restart Import Export Service | Saurabh
Attach Prime main company backup as archive on Stage - from Do not delete before any activity | Indra & Ashwin |  | NA
Convert CA to partners | Saurabh
Assign rights to Partner for new company | Saurabh
Assign rights to company admin / create new admin for new company | Saurabh
Inform client for completion of entire process | Saurabh | 18:00

## Checkpoints
Checkpoints for new Standalone company for "EHMC" | Status
Take Back up of "Prime Healthcare" for future reference
Create new company with name "EHMC"
Move all employees , dependents & election data with History
Move all customization settings for all Admin based screens such as - Plan, Rate, Date rules, etc
Recalculate eligibility rules
Activate EHMC on Production
Update company information screen for Module mapping & EDS workflow screens
Update EDI templates & schedules
Remove all Company Admin access from EHMC
Convert the list of Company Admin login to Partner roles (List shared by Jennifer )
Assign rights for EHMC to the partner role users
Enable employee login on EHMC
Enable CDC for HR simplified COBRA files
Verify all login roles & workflow, reports, EDI
Verify themes, company files, logo, fileserver records
Checkpoints for Prime legacy company post split on "Prime Healthcare" | Status
On "Prime Healthcare" - disbale employee login for EHMC employees
Remove access of EHMC from "Prime Healthcare" for all company Admin users
Remove EHMC class from all templates for "Prime Healthcare"
Verify all EDI feed customization & Schedules
Verify all login roles & workflow, reports, EDI

## Testing Plan
Sr. No. | Testing plan for both companies - Prime Healthcare & EHMC
1 | Employee Open Enrollment workflow.
2 | Employee New Hire workflow.
3 | Employee Qualifying event workflow.
Traverse all pages Partner and Admin Login (Smoke Testing, Add, Delete and Update Functions)
4 | Classes
5 | Rates
6 | Add/ Change plan design
7 | Rate plan design mapping
8 | Form Builder
9 | Configure landing page
10 | Qualifying event
11 | Company information(New Hire/Rehire) (All Tabs)
12 | Payroll schedule
13 | View History
14 | Add Employee
15 | Search Employee
16 | Review Changes
17 | Pending EOI
18 | Review Dependent audit
19 | Pending Queue
20 | Review Employee document
21 | All reports
22 | Template Management / Scheduled feeds
23 | Widgets, Counters and Tiles
24 | Enrollment for Prime Class, Eligibility
25 | Admin activities like Enrollment in QE, OE, Report run etc.
Employee Login
1 | Widgets and Tiles
2 | Reports, Confirmation Statements etc
**Smoke Testing, Add, Delete and Update Functions for above points