## Summary - Production move EHMC
Prime breakout plan for standalone "Encino Hospital Medical Center" | Company Details
Company Name : EHMC | Master / Legacy Company Name | Prime Healthcare
Move Date: 09th July 2016 | Company Name | EHMC
Black Out Start Date Time: Friday' 08th July 2016 07:30 PM PST | DB Name | Prime_Encino_Hospital_Medical_Center_12381
Black Out End Date Time: Saturday' 09th July 2016 06:00 AM PST | New Company ID | 12381
Contingency Plan
In case this split activity results in any issue, Back up of "Prime Healthcare" taken on start of blackout will be restored and company will be live without any change of data / customization.
Assumptions / Additional points discussed
"Prime Healthcare" will not be available during the mentioned blackout period
All midnight services will be executed only after breakout for EHMC is complete
Scheduled feeds for "Prime Healthcare" will be executed after completion of this activity
From Prime legacy company i.e "Prime Healthcare" we are only deactivating employee/company admin access for EHMC as of now until we receive a go ahead from cleint to remove this separated out class & related data entirely from legacy company
Respective AE will take care of assigning Company Admin rights / creating new CA login if required.
All EDI people, client will be notified by AE not to import / acess anything related to separated out class from Prime legacy company as it will still be acessible to Partner / Broker & SA roles. [ Until it is removed after approval ]
Access policy for Partners - No need to create any new partner this time

## Classes
Class2ID
19,42,6,5,41,4,11
Class 1 / Facility |  | Class 2 / Classification
ID | Name | ID | Name
19 | Encino Hospital Medical Center | 4 | Full Time Employees
|  | 5 | Part Time Employees
|  | 6 | Per Diems
|  | 11 | Physicians
|  | 15 | CFOFT CNA | Remove
|  | 19 | Csuite
|  | 41 | SEIU 121 Full Time
|  | 42 | SEIU 121 Part Time

## Feeds
Template to be removed
Templates moved to global level
List of all feeds on Prime with Class , Grouping & Schedule details - Encino Hospital Medical Center
Status | Template ID | Template Name | Group Template Name | Last Export Date | Schedule Type | Schedule Day | Global Level Schedule | Interval Period | Start Date Time | Class1 IDs | Class2 IDs
Scheduled | 10 | Prime Healthcare Services_Keenan_Eldorado 834 5010 | Prime Healthcare Services_Keenan_Eldorado 834 5010_Group | 2016-07-04 09:01 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,13,44,14,15,42,40,41,51,36,37,52,16,43,27,28,7,38,57,60,35,34,17,29,30,20,21,58,53
Scheduled | 180 | MediTech CS Encino Hospital Medical Center | _Prime MediTech CS Encino Hospital Medical Center | 2016-07-04 05:56 |  |  | Daily with Interval | 0 |  | 19
Scheduled | 495 | Global Search Member | Prime Global Search Member | 2016-06-30 15:31 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,7,48,38,57,60,35,34,17,29,30,20,21,58,53
Scheduled | 387 | NEW HR Simplified COBRA Participant | Prime Healthcare_NEW HR Simplified COBRA Participant_Group | 2016-06-30 15:21 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,32,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 386 | NEW HR Simplified COBRA DEPENDENT | Prime Healthcare_NEW HR Simplified COBRA DEPENDENT_Group | 2016-06-30 15:11 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,32,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 385 | NEW HRSimplified_COBRA Coverage | Prime Healthcare_NEW HRSimplified_COBRA Coverage_Group | 2016-06-30 15:01 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,32,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 26 | Hyatt Legal | Prime Healthcare_Hyatt Legal_Group | 2016-06-30 10:04 |  |  | Weekly | 0 |  | 0,26,8,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,36,37,52,16,61,43,27,28,7,38,57,60,35,34,17,29,30,20,21,58,53
Scheduled | 24 | DeltaCare HMO 834 5010 | Prime Healthcare_DeltaCare HMO 834 5010_Group | 2016-06-30 08:21 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,46,49,22,47,45,13,44,14,15,42,40,41,51,36,37,52,16,43,27,28,56,7,31,33,48,55,38,57,32,35,34,17,29,30,20,21,53,50
Scheduled | 12 | Delta Dental PPO 834 5010 | Prime Healthcare Delta Dental PPO 834 5010_Group | 2016-06-30 07:31 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,38,57,35,34,17,29,30,20,21,58,53
Scheduled | 486 | Davis Vision Eligibility_Subscriber | Prime Healthcare_Davis Vision | 2016-06-30 07:08 |  |  | Weekly | 0 |  | 0,26,8,9,10,0,54,11,12,19,46,49,22,47,45,13,44,14,15,23,42,40,41,24,51,59,36,37,52,16,61,43,27,28,56,7,31,33,48,55,38,57,32,60,35,34,17,29,30,20,21,58,53,50,25
Scheduled | 487 | Davis Vision Eligibility_Dependents | Prime Healthcare_Davis Vision | 2016-06-30 07:08 |  |  | Weekly | 0 |  | 0,26,8,9,10,0,54,11,12,19,46,49,22,47,45,13,44,14,15,23,42,40,41,24,51,59,36,37,52,16,61,43,27,28,56,7,31,33,48,55,38,57,32,60,35,34,17,29,30,20,21,58,53,50,25
Scheduled | 17 | Prime Healthcare Services VSP_834 5010 | Prime Healthcare Services VSP_834 5010_Group | 2016-06-30 06:11 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,38,57,35,34,17,29,30,20,21,53
Scheduled | 23 | Aetna Lower Bucks 834 5010 | Prime Healthcare_Aetna Lower Bucks 834 5010_Group | 2016-06-30 06:06 |  |  | Weekly | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
Scheduled | 31 | MetLife_Dental_5010 834_Prime Healthcare Services | Prime Healthcare _MetLife_Dental_5010 834_Group | 2016-06-29 09:43 |  |  | Weekly | 0 |  | 0,19,22,47
Scheduled | 2 | Prime Healthcare Services HR Simplified FSA and DCA feed | Prime Healthcare Services HR Simplified FSA and DCA feed | 2016-06-29 06:03 |  |  | Weekly | 0 |  | 26,8,0,9,10,0,11,12,19,46,49,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,33,38,57,60,35,34,17,29,30,20,21,58,53,50
| 510 | HR Simplified FULL FSA |  | 2016-06-29 03:19 |  |  |  | 0 |  | 0,26,8,9,10,11,12,19,46,49,22,47,45,13,44,14,15,42,40,41,36,37,52,16,43,27,28,7,33,38,57,60,35,34,17,29,30,20,21,58,53,50
Scheduled | 221 | Sun Life EOI_EHMC | Prime_SunLife_EOI_Group | 2016-06-24 07:00 |  |  | Weekly | 0 |  | 19
| 426 | EDI Audit VSP | Prime Healthcare_EDI Audit VSP_Group | 2016-05-09 10:17 |  |  |  | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,7,48,38,57,60,35,34,17,29,30,20,21,58,53
| 423 | EDI Audit Delta Dental PPO | Prime Healthcare_EDI Audit Delta Dental PPO_Group | 2016-05-09 09:24 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 21 | HR Simplified_COBRA_Coverage |  | 2016-03-24 05:34 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57
| 422 | _EBS AddChangeTerm |  | 2016-03-08 17:45 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 472 | EDI Audit Aetna |  | 2016-01-06 21:54 |  |  |  | 0 |  | 26,8,0,9,10,0,11,12,19,22,47,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,7,48,38,57,60,35,34,17,29,30,20,21,58,53
| 432 | Test |  | 2015-12-23 02:07 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 424 | EDI Audit DeltaCare HMO | Prime Healthcare_EDI Audit DeltaCare HMO_Group | 2015-12-07 18:03 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 20 | HRSimplified_COBRA_Dependent |  | 2015-08-06 07:34 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56
| 19 | HR Simplified_COBRA_Participant |  | 2015-08-06 07:24 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56
| 200 | zDependent Audit Data Demographic Census (do not use) |  | 2014-12-23 15:50 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 60 | Enrollment Counts | Prime_Enrollment Counts_Group | 2014-10-12 18:18 |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 41 | Lawson | Lawson_Group |  |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 85 | LHP Payroll Supp Life | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 86 | LHP Payroll File Voluntary Life | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 382 | Equifax Employee Benefits Worksheet | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 383 | Equifax Dependent Benefit Worksheet | Prime_Equifax Dependent Benefit Worksheet_Group |  |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 384 | Equifax Employee Benefit Worksheet Waives | Prime_Equifax Employee Benefit Worksheet Waives_Group |  |  |  |  | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 421 | Prime Health HNAS 834 5010 | [5 empty] | 0 |  | 26,8,0,9,10,0,54,11,12,19,22,47,13,44,14,15,42,40,41,51,59,36,37,52,16,61,43,27,28,56,7,48,55,38,57,60,35,34,17,29,30,20,21,58,53
| 425 | _EBS COBRA Terms weekly | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 436 | Test_Clone | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 442 | EBS Newly Enrolled COBRA | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61
| 452 | MediTech CS Encino Hospital Medical Center_Life | [5 empty] | 0 |  | 19
| 480 | test prime imputed amount | [5 empty] | 0 |  | 7,8,9,10,11,12,13,14,15,16,17,0,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,0,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61

## Split steps Master Plan
Milestones marked in yellow color
Task Description | Owner | Cut off time | Status
Pre-requisites
Check list of Class1 & Class2 values to keep on new company | Saurabh | 2 days prior | Done
Check list of Class2 values to keep on Main Prime company | Saurabh | 2 days prior | Done
Intimate for Black out date & time to all stakeholders | Saurabh | 2 days prior | Done
Check all scheduled feeds for New group company & Prime Healthcare | Saurabh | 2 days prior | Done
Create Group level templates for new group - 1 day in advance | Hrishikesh | 2 days prior | Not Required
Network support engineer availability check & Team availability check | Samir / Satya / Sachin | 1 week prior | Done
Keep scripts compiled and ready for Production | Ashwin | 1 days prior | Done
Add config changes for Import Export config on production for new company tag | Rohan | 2 days prior | Done
Save Class1 & Class2 values on Export templates for Prime Healthcare where ever criteria is null / none | Saurabh | 2 days prior | Done
Server activities |  |  | Done
Stop Import Export Scheduler service | Ashwin | 9:00 | Done
Inactive Prime Healthcare - main company | Ashwin | 9:00 | Done
Delete CDC for Prime Healthcare main company | Indra | 9:00 | Done
Start Import Export Scheduler service for other company feeds to pick up | Ashwin | 9:00 | Done
Take backup of Prime Healthcare & Online Enrollment and keep in DO NOT Delete | Indra | 9:00 | Done
Attach this back up manually with Name "EHMC" on Production | Indra | 9:00 | Done
Add entry in OnlineEnrollment > Company table, keep company inactive | Ashwin | 10:00 | Done
Copy assets and files on web / file server with new company ID Generated Files (sequence-bar etc), Images,Stylesheet and Forms(File Server) | Ashwin | 10:00 | Done
ON CLUSTER Only Need to Give rights to SA user for this company to Dashboard [Default Rights to Dashboard while company migrating from stage to production.sql] | Ashwin | 10:00 | Done
Execute company split scripts and steps | Saurabh |  | Done
Activate this new Company on production | Saurabh | 11:30 | Done
Generate all eligibility criteria using Workterra Utility | Saurabh | 11:30 | Done
Save EDS pages, selection Module on Module mapping screen, save theme | Saurabh | 11:30 | Done
Save Theme from Site branding & theme (Theme for Prime Healthcare) | Saurabh | 11:30 | Done
Save Dashboard configuration for Employees, Partner, Company Admin | Saurabh | 11:30 | Done
Upload logo for EHMC company | Saurabh | 11:30 | Done
Remove Classwise images for other classes | Saurabh | 11:30 | Done
Create user access policy for new partners | Saurabh | 11:30 | Not Required
Move PGP Keys to Global level | Saurabh | 11:30 | Not Required
Add company ID in service configuration file- Workterra service scheduler | Ashwin | 11:30 | Done
Open company for QA Testing | Saurabh | 11:45 | Done
Execute Workterra scheduler service for new company | Ashwin | 12:00 | Done
Initial approval from QA for no breaking points | Hrishikesh | 13:00 | Done
Deactivate respective class from Prime Healthcare main company on production | Saurabh |  | Done
Handover Prime Healthcare main company to QA for testing except reports | Saurabh | 14:00 | Done
Feeds creation and scheduling | Hrishikesh | 14:30 | Done
Verify export feed schedules | Rohan | 14:30 | Doen
Enable CDC on New company | Indra | 16:00 | Done
Enable CDC for Prime Healthcare | Indra | 16:00 | Done
Verify reports after replication is up | Hrishikesh | 17:30 | Done
QA Approval for entire process | Hrishikesh | 17:30 | Done
Restart Import Export Service | Saurabh |  | Done
Attach Prime main company backup as archive on Stage - from Do not delete before any activity | Indra & Ashwin |  | NA
Convert CA to partners | Saurabh |  | Not Required
Assign rights to Partner for new company | Saurabh |  | Done
Assign rights to company admin / create new admin for new company | Saurabh |  | Not Required
Inform client for completion of entire process | Saurabh | 18:00 | Done

## Partners
List of all Partner / Broker Users for EHMC
UserName | Role | FirstName | LastName | EmailAddress | EHMC
achoi | Partner | Art | Choi | achoi@Keenan.com | Yes
Agarvey | Partner | Amanda | garvey | Amanda.garvey@ebsebenefits.com | Yes
amberjones | Partner | Amber | Jones | amber.jones@ebsbenefits.com | Yes
amitt | Partner | Amit | Thorve | amit.thorve@ebsbenefits.com | Yes
amjohnson | Partner | Amannda | Johnson | amanda.johnson@ebsbenefits.com | No
aretana | Partner | Annette | Retana | aretana@primehealthcare.com | Yes
cellenberger | Partner | Chris | Ellenberger | chris.ellenberger@ebsbenefits.com | Yes
crhodes | Partner | Chimane | Rhodes | chimane@ebsbenefits.com | Yes
cteran | Partner | Celia | Teran | celia.teran@ebsbenefits.com | Yes
cwibbing | Partner | Cindy | Wibbing | cindy.wibbing@ebsbenefits.com | Yes
Daniels | Partner | Daniel | Suguitan | daniel.suguitan@ebsbenefits.com | No
DDOlek | Partner | Dee Dee | Olek | deedee.olek@ebsbenefits.com | Yes
deb | Partner | Debbie | Kulling | debbie.kulling@ebsbenefits.com | No
dgreen | Partner | Daphne | Green | dgreen@keenan.com | Yes
djenkins | Partner | Denielle | Jenkins | denielle.jenkins@ebsbenefits.com | Yes
dVelasquez | Partner | Damion | Velasquez | Damion.Velasquez@ebsbenefits.com | Yes
dwilliams | Partner | Denise | Williams | dwilliams@Keenan.com | Yes
ecompton | Partner | Erendira | Compton | ecompton@keenan.com | Yes
eelliott | Partner | Erika | Elliott | EElliott@primehealthcare.com | Yes
emmamondragon | Partner | Emma | mondragon | emma.mondragon@ebsbenefits.com | No
eroche | Partner | Elisa | Roche | eroche@keenan.com | Yes
flogoai | Partner | Francine | Logoai | flogoai@primehealthcare.com | Yes
hsanford | Partner | Heather | Sanford | hsanford@keenan.com | Yes
hthomas | Partner | Helen | Thomas | hthomas@keenan.com | Yes
jeharris | Partner | Jeshurun | Harris | jeshrun.harris@ebsbenefits.com | No
jfernandes | Partner | Jennifer | Fernandes | Jennifer.fernandes@ebsbenefits.com | Yes
jleugers | Partner | Jennifer | Leugers | jennifer.leugers@ebsbenefits.com | Yes
jphilp | Partner | Jennifer | Philp | jennifer.philp@ebsbenefits.com | No
jtessen | Partner | Janice | Tessen | jtessen@keenan.com | Yes
jyoon | Partner | Jenny | Yoon | jyoon@keenan.com | Yes
ketyler | Partner | Kevin | Tyler | kevin.tyler@ebsbenefits.com | No
kevinw | Partner | Kevin | Walker | kevin.walker@ebsbenefits.com | No
kgaillant | Partner | Kelli | Gaillant | kelli.gaillant@ebsbenefits.com | Yes
kmejia | Partner | Kari | Mejia | kari.mejia@ebsbenefits.com | No
kmendez | Partner | Kimberly | Mendez | kmendez@primehealthcare.com | Yes
kthomson | Partner | Kimberly | Thomson | kthomson@primehealthcare.com | Yes
levans | Partner | Letty | Evans | levans1@keenan.com | Yes
LisaDavison | Partner | Lisa | Davison | lisa.davison@ebsbenefits.com | No
lmartinez | Partner | Luis | Martinez | luis.martinez@ebsbenefits.com | Yes
lwolfswinkel | Partner | Leslie | Wol | lwolfswinkel@primehealthcare.com | Yes
mburke | Partner | Mary | Burke | mburke@keenan.com | Yes
mcoates | Partner | Michael | Coates | mcoates@keenan.com | Yes
mdavis | Partner | Melissa | Davis | mdavis2@keenan.com | Yes
mdemla | Partner | Monika | Demla | monika.demla@ebsbenefits.com | Yes
mkelly | Partner | Maria | Kelly | mkelly@keenan.com | Yes
mramirez | Partner | Maria | Ramirez | mramirez@keenan.com | Yes
msayao | Partner | Michelle | Sayao | Michelle.Sayao@ebsbenefits.com | No
msepulveda | Partner | Marta | Sepulveda | msepulveda@keenan.com | Yes
mwoods | Partner | Marquies | Woods | mwoods@keenan.com | Yes
nlavoie | Partner | Natalie | Lavoie | nlavoie@keenan.com | Yes
omencias | Partner | Ofelia | Mencias | omencias@keenan.com | Yes
palmeida | Partner | Phil | Almeida | phil.almeida@ebsbenefits.com | No
pwass | Partner | P-Kay | Wass | pwass@keenan.com | Yes
RABaker | Partner | Rachel | Baker | rachel.baker@ebsbenefits.com | Yes
rthomas | Partner | Rochelle | Thomas | Rochelle.Thomas@ebsbenefits.com | No
sallisonprod | Partner | Steve | Allision | steve.allision@ebsbenefits.com | Yes
sford | Partner | Sawanna | Ford | sford@keenan.com | Yes
sjones | Partner | Stacy | Jones | sjones1@Keenan.com | Yes
skralka | Partner | Shannon | Kralka | skralka@keenan.com | Yes
snobunaga | Partner | Sandy | Nobunaga | SNobunaga@Keenan.com | Yes
spowers | Partner | Samantha | Powers | spowers@primehealthcare.com | Yes
ssato | Partner | Shelby | Sato | ssato@keenan.com | Yes
suwilliams | Partner | Susan | Williams | susan.williams@ebsbenefits.com | Yes
tifisher | Partner | Tiquanna | Fisher | Tiquanna.Fisher@ebsbenefits.com | No
tjimenez | Partner | Thomas | Jimenez | tjimenez@primehealthcare.com | Yes
tlee | Partner | Tony | Lee | tlee@keenan.com | Yes
tponsiano | Partner | Trisha | Ponsiano | Trisha.Ponsiano@ebsbenefits.com | No
trmitch | Partner | Tracy | Mitch | Tracy.Mitch@ebsbenefits.com | No
tross-mcdaniel | Partner | Treraza | Ross-Mcdaniel | tross-mcdaniel@keenan.com | Yes
TSimpson | Partner | Traci | Simpson | traci.simpson@ebsbenefits.com | Yes
ttarvin-roberts | Partner | Tamya | Tarvin-Roberts | ttarvin-roberts@keenan.com | Yes
tvalle | Partner | Tammy | Valle | tvalle@primehealthcare.com | Yes
urgomez | Partner | Ursula | Gomez | Ursula.Gomez@ebsbenefits.com | Yes
vnguyen | Partner | Van | Nguyen | Van.nguyen@ebsbenefits.com | Yes
ymacshate | Partner | Yashau | Macshate | yashua.macshate@ebsbenefits.com | Yes

## Additional Changes
Description | Status
Guides and PCP Directories were added | Done
The rates were updated for EPO RX1, EPO RX2 and Value Plans
The rates were updated for EPO2 RX1
The rates were updated for PPE RX1
The Voluntary AD&D Dependents and Child plans were changed to add in the extra eligibility | Done
Combined Vol LTD/STD rate was updated
CHMC plans were removed from QE
Opt Out credit rate was updated
EAP eligibility was updated to include PD | Done
Removed Hourly Monroe from the payroll schedule | Done
Updated eligibility for Value Plan to include FT SEIU & PD | Done
The rates were updated for the PPO plans
Metlife PPO rate was updated
Metlife Preventive rate was updated
Optional Life rate was updated
Optional Spouse and Child Life plans were updated
Child and Spouse Voluntary AD&D rates were updated

## Checkpoints
Checkpoints for new Standalone company for "EHMC" | Status
Take Back up of "Prime Healthcare" for future reference | Done
Create new company with name "EHMC" | Done
Move all employees , dependents & election data with History | Done
Move all customization settings for all Admin based screens such as - Plan, Rate, Date rules, etc | Done
Recalculate eligibility rules | Done
Activate EHMC on Production | Done
Update company information screen for Module mapping & EDS workflow screens | Done
Update EDI templates & schedules | Done
Remove all Company Admin access from EHMC | Done
Convert the list of Company Admin login to Partner roles (List shared by Jennifer ) | Done
Assign rights for EHMC to the partner role users | Done
Enable employee login on EHMC | Done
Enable CDC for HR simplified COBRA files | Done
Verify all login roles & workflow, reports, EDI | Done
Verify themes, company files, logo, fileserver records | Done
Checkpoints for Prime legacy company post split on "Prime Healthcare" | Status
On "Prime Healthcare" - disbale employee login for EHMC employees | Done
Remove access of EHMC from "Prime Healthcare" for all company Admin users | Done
Remove EHMC class from all templates for "Prime Healthcare" | Done
Verify all EDI feed customization & Schedules | Done
Verify all login roles & workflow, reports, EDI | Done

## Testing Plan
Sr. No. | Testing plan for both companies - Prime Healthcare & EHMC
1 | Employee Open Enrollment workflow. | Done
2 | Employee New Hire workflow. | Done
3 | Employee Qualifying event workflow. | Done
| Traverse all pages Partner and Admin Login (Smoke Testing, Add, Delete and Update Functions) | Done
4 | Classes | Done
5 | Rates | Done
6 | Add/ Change plan design | Done
7 | Rate plan design mapping | Done
8 | Form Builder | Done
9 | Configure landing page | Done
10 | Qualifying event | Done
11 | Company information(New Hire/Rehire) (All Tabs) | Done
12 | Payroll schedule | Done
13 | View History | Done
14 | Add Employee | Done
15 | Search Employee | Done
16 | Review Changes | Done
17 | Pending EOI | Done
18 | Review Dependent audit | Done
19 | Pending Queue | Done
20 | Review Employee document | Done
21 | All reports | Done
22 | Template Management / Scheduled feeds | Done
23 | Widgets, Counters and Tiles | Done
24 | Enrollment for Prime Class, Eligibility | Done
25 | Admin activities like Enrollment in QE, OE, Report run etc. | Done
Employee Login
1 | Widgets and Tiles | Done
2 | Reports, Confirmation Statements etc | Done
| **Smoke Testing, Add, Delete and Update Functions for above points | Done