## Open
MATT Construction HCM Open Items
Issue Start Date | Issue Description | Status | Jira Ticket # | Date Issue Closed
OPEN
2016-08-26 | Remove Cell phone pages | 8/29 - MATT requested Cell phone page be removed from OnBoard as this is no longer an option. KS has sent to Development
2016-04-01 | Upload resume and employee photo during Onboard | Suggestion sent to Development by DM. 8/29 - Dev has below questions for MATT to see if this is possible. 1. Resume upload & Employee photo should be uploaded by Employee only or by Partner / CA also ? 2. For uploading photo, would admin approval be required?
2016-07-26 | MATT Onboard review notes and follow up
| Email examples - what Employee will receive | Log-In with Partner/Admin credentials - Go to company home page - On left side menu click on Communications-Email Message Format - Select Category and you will find desired template. - Add Employee - (click on this and it will show you the text sent to the employee)
| Employee Add page - change receive email to default to YES | MATT would like the receive emails option to default to yes. Development is looking at this however most likely not possible. MATT can add to their internal process for required elements when adding an employee
| Wage notice | MATT requested this page to be removed.
| Remote wipe page - remove boxes and replace with just dashes | To the right - please remove characters from the 3 listed options
| Ben Admin Tunnel changes | First page with Materials and Resources to be removed  This is page #4 on the Ben Admin Employee tunnel o Can this Materials and Resources be replaced with the forms library? 8/15 - Dev requested test by MATT to view and approve before moving to stage environment. 8/29 - KS resent username and password for testing and approval
| Ben Admin home page | MATT asked if there is a way to see the employee home page before completing Ben Admin Tunnel. Dev reported this is not possible. 8/24 - Valerie is updating language for Ben Admin page and will send to KS
| Benefit Guide updates | KS sent to Dev. This is updated
| I-9 process verification | MATT team asked for further instruction on I-9 process. Provided detail to MATT in instruction manual. They will not have a login as system will auto open eVerify when they approve. All forms will be in WT. They will keep copies of DL and SS Card on file.
| Reports for answers to survey questions, business cards, etc. | Development is creating a report MATT will run to review
| Harrassment Policy page set up | KS sent Harrassment Policy information to development. Created and reviewed by MATT. Requested removal of the signature requirement if the password is required. 8/29 - KS confirmed with Dev that the password is required and requested the signature to be removed and only require employee to type name for signature to align with other pages.

## Closed
CLOSED
| Wage Works FSA file | In Test (CE) - Test file sent 1/8. 1/11 - test file sent. 1/12 - Waiting for test to be approved so production file can be sent. Production File sent 1/12. |  | 2016-01-12
2015-11-30 | C. Richins newborn son Austin on UHC discrepancy report (Dental/Vision) | 12/1 - DM clarified DOB and enrollment dates for EDI. 12/30 - UHC under the impression that enrollment is outside 60 day retro period. 1/6 - DM requested file screen shot for UHC. UHC denied coverage. DM emailed appeal. 1/14 - Appeal approved. Child has full coverage. |  | 2016-01-14
2016-01-22 | Aon req Enrollment Report to be used for OE prep. | 1/22 - DM sent report based on template provided. |  | 2016-01-22
| New Hire FSA is calculating correctly (based on 13 pp plan life) but all other benefits are not calculating on 26 pp rates. | 1/25 - DM sent urgent message to DR and Dev asking for fix. 1/27 - Dev returned fix. All okay except HDHP plan. Sent back to Dev w/ P1. 1/29 - Client is statisfied with issue fix. |  | 2016-01-29
| Ceridian COBRA File | In Test - 1/4 - New test file sent. 1/5 Ceridian not seeing file. 1/8 - Ceridian found file. 1/11 Per Ceridian, file named incorrectly. DM req Dev to rename and resend. 1/12 - File resent. DM to alert Claudia & Peter @ Ceridian. 1/13 Ceridian rec'd file. will review/results expected 1/14. 1/18 - Dev says they can not send test files to carrier FTP even though they have 2-3 time in the past. DM to discuss w/ JL. New test file sent 1/19. 1/22 - New file has been sent. 1/25 - Ceridian conf receipt of file. 1/27 - Carrier question re: 2 files (QE/NH). DM ref to PA for decision. Carrier post-review comments sent to Dev/EDI. 1/29 - Test files passed. Waiting for Schedule and 1st production file to be sent. 2/9 - Scheduled Weekly, Tue 8am. Ceridian has confirmed receipt of first files (2). |  | 2016-02-09
2016-02-01 | 3 employees are showing no premium amt for Vol Life and are in Pending EOI. | 2/9 - DM opened ticket and informed client of status. 2/10 - Dev discovered that the Ees did not complete the Tobacco Use Survey. Once yes/no is provided by VY, DM will update WT and have rates recalculated. | WT-593 | 2016-02-10
2016-01-25 | Enrollment (AKA CENSUS) report in horizonal format | 1/28 - Development was able to produce report in requested format. Broker has asked for additional columns. DM to work on. 2/2 - DM sent revised report. 2/5 - SF asked DM to keep on the agenda.
2016-02-22 | Matthew Reeves - NH not showing on UHC file | 2/22 - DOH - 2/1; DOE - 2/11; Eff 3/1. DM opened ticket. 2/29 - Will go on 2/26 file. Still wondering why so late?
2016-02-24 | No Waive/Enroll | 2/24 - 3 EE's do not show waive or enroll forvarious plans. N. Furbeyer - Due to Vyost terminating enrollment. J Chao/M Cerrina did not go through OE tunnel. Did not waive or enroll in Flex. Aon to confirm what action to take. Also, upon confirmation by MATT, will change plans to No Action = Waive in WT prior to OE.
2016-02-25 | Ceridian (WageWorks aquisision) COBRA File | 2/25 - Aon informed EBS that eff 3/1 Ceridian has been aquired by WageWorks. DM to monitorsuccess of file feeds on 3/1 and report to Aon. Aon to provide new contact info and acct # to EBS.
2016-05-03 | Unable to approve pending enrollment | 5/3 - KS opened Jira ticket. AM reported having same issue last week with diff. client. | Pending
| Unum STD/LTD File | In Test (Dev) - 1/6 Changes req. 1/7 - test file sent. 1/13 - DM sent email to Samir req update. 1/18 - Per carrier 1/7 file never rec'd. 1/19 - New test file sent, but not rec'd by UNUM. 1/20 - DM found past FTP info. Sent email to Dev to confirm that is where they are sending it. Also emailed past carrier EDI analyst (cc current who could not confirm info) to try to confirm FTP info. 1/21 - UNUM rec'd file, but cant read in current format. Req in cvs/excel as done in past. Sent req to Dev to resend. Dev sent in correct format. Jenna confirmed rec'd. 1/26 - Jenna returned comments. DM sent to Dev & Phil. 2/9 - New test file being sent today. 2/12 - Comments rec'd from Unum. 2/19 - New test file sent. 2/24 - No comments rec'd. Aon sent response req to Unum. 2/26 - Comments rec'd. 3/3 - New test file sent. 4/1 - last test file sent 3/21. Comments rec'd 3/25. New carrier EDI contact. 4/13 - New Test file sent XXX. It was discovered that Unum had updated salaries and WT did not. VY approved upload of updated salaries to WT. DM working with EDI to complete task. | EDI-268 | 2016-04-28
| Stephen Montoya - No Admin notification when EE change marital status and terminated cov for ex-spouse. | Per Dev, QE is set up correctly. Waiting for Dev to explane cause. | WT-1831 | 2016-05-03
| UHC Life File | In Test - 1/6 Dev sent test file to Heath FTP. Life EDI person will retreive. Waiting for Life FTP to be set up. Will forward to Dev when rec. 1/15 - CE sent carrier file change request to Dev. 1/19 - New test file sent on 1/15. We rec'd comment and are working on file. 1/20 - DM sent Dev comments/questions to Chris to coord with UHC contact. 1/22 - DM provided Dev with facets and formatting information from carrier. 1/27 - Dev had questions re: Plan IDs etc. DM replied. 2/2 - Per Amit, new test tile ready to go. 2/4 - DM req conf from PA that test file was sent. 2/9 - New test file being sent today. 2/17 - Comments rec'd from carrier. 2/23 - DR approved 2 enhancements. Dev working on file. 4/1 - Most recent rest file sent 3/9. Close to production. | EDI-50 | 2016-05-06
| Client req QE Audit | Client made changes to QE set-up. Need to test. Per Aon, okay to call complete. |  | 2016-05-13