## Open
MATT Construction HCM Open Items
Issue Start Date | Issue Description | Status | Jira Ticket # | Date Issue Closed | Owner | Client Feedback | MATT Approval
OPEN
2016-08-26 | Remove Cell phone pages | 8/29 - MATT requested Cell phone page be removed from OnBoard as this is no longer an option. KS has sent to Development 9/1 KS confirmed Valerie only wants the cell phone order page to be removed and to keep the policy in place. KS sent to Development | WT-610 | 2016-09-08 | Development
2016-04-01 | Upload resume and employee photo during Onboard | Suggestion sent to Development by DM. 8/29 - Dev has below questions for MATT to see if this is possible. 1. Resume upload & Employee photo should be uploaded by Employee only or by Partner / CA also ? 2. For uploading photo, would admin approval be required? 9/2 - Per VY upload of photo and resume should be completed by EE. No Admin approval required | WT-1709 |  | Development
2016-07-26 | Wage notice | MATT requested this page to be removed. 9/1 - KS confirmed with DEV the page that should be removed. DEV AE is verifying if we can just remove WAGE calculation This has not been removed, the only item removed was the wage calculation. Please remove entire Wage information page "Notice to Employees" It is removed please reverify | WT-610 |  | Development
2016-07-26 | Ben Admin home page | MATT asked if there is a way to see the employee home page before completing Ben Admin Tunnel. Dev reported this is not possible. 8/24 - Valerie is updating language for Ben Admin page and will send to KS 8/30 - Valerie provided updated language. KS sent to development 9/2 - Development is updating language on Materials and Resources page per request from MATT ON Ben Admin page 4, it says "Please read the benefit program summary included in the forms library by clicking on the link below." There is no link that I can see. Remove this language. Add all forms in ZIP folder attached on 7/27/16 to the Forms Library. These are in production under Ben Admin. Want to make sure these will be in forms libraary once this is moved from stage to production. The exception in this zip file that should not be in the forms library is "ending page A" from the library as it is not needed as a reference Which page you are reffering to ? Also, provide us the language. Once you let us know the page details and the required language we'll update this. For adding forms that we received in Zip folder- this is done on stage,as per discussion we had in this context earlier "ending page A" was not incorporated for this implementation. Once we receive Sign-Off from you and MATT, the whole implementation will move to production which includes mpving these forms to library as well. Please eloborate more on These are in production under Ben Admin part of above comments. | WT-610 |  | Development
2016-07-26 | Reports for answers to survey questions, business cards, etc. | Development is creating a report MATT will run to review 9/1 - Reports can be run under standard reporting. Employee census. Choose the fields for each of the questionaire page MATT want to review. | WT-610 | 2016-08-15 | EBS/MATT
2016-07-26 | Harrassment Policy page set up | KS sent Harrassment Policy information to development. Created and reviewed by MATT. Requested removal of the signature requirement if the password is required. 8/29 - KS confirmed with Dev that the password is required and requested the signature to be removed and only require employee to type name for signature to align with other pages. 9/6/16 - Swapnil confirmed language can be added under the password stating "enter password used at login". THe signature and password will be added to all signature required pages in place of text box 9/9/16 - Electronic signature not updated on each page, missing from I9, W4 page, Safety Policy Statement, Drug and Alcohol Policy, Mobile Device Acceptable Use policy (3 areas). Remove box to type name from Harrassment Policy also does not default today's date like the rest of the pages. Needs Discussion, signature from other forms is removed as a part of requirement shared earlier. For Harrasment policy- this form being added newly/recently signature field is present on this and hence necessary corrections were made as per your comments regarding adding language. | WT-610 |  | Development
2016-09-06 | Required fields for data entry boxes | Dev will add text in all data entry boxes ex. DOB and phone number required fields Text only shows to add numbers but not if they need dashes or slashes This text is added just for reference. If any other text needs to be added then please provide us the language-words-format for same. | WT-610 |  | Development
ON Ben Admin page 4, it says "Please read the benefit program summary included in the forms library by clicking on the link below." There is no link that I can see. Remove this language.
Add all forms in ZIP folder to the Forms Library….

## Closed
CLOSED
2016-07-26 | Email examples - what Employee will receive | Log-In with Partner/Admin credentials - Go to company home page - On left side menu click on Communications-Email Message Format - Select Category and you will find desired template. - Add Employee - (click on this and it will show you the text sent to the employee) | WT-610 | 2016-08-09
2016-07-26 | Benefit Guide updates | KS sent to Dev. This is updated | WT-610 | 2016-08-03
2016-07-26 | I-9 process verification | MATT team asked for further instruction on I-9 process. Provided detail to MATT in instruction manual. They will not have a login as system will auto open eVerify when they approve. All forms will be in WT. They will keep copies of DL and SS Card on file. | WT-610 | 2016-07-26
2016-07-26 | Remote wipe page - remove boxes and replace with just dashes | To the right - please remove characters from the 3 listed options | WT-610 | 2016-08-29 | Development
2016-07-26 | Employee Add page - change receive email to default to YES | MATT would like the receive emails option to default to yes. Development is looking at this however most likely not possible. MATT can add to their internal process for required elements when adding an employee 8/31 - This is not a change that can be made. MATT will add to their internal process | WT-610 | 2016-08-31 | EBS/MATT
2016-07-26 | Ben Admin Tunnel changes | First page with Materials and Resources to be removed  This is page #4 on the Ben Admin Employee tunnel o Can this Materials and Resources be replaced with the forms library? 8/15 - Dev requested test by MATT to view and approve before moving to stage environment. 8/29 - KS resent username and password for testing and approval 9/1 - Valerie approved HSPL changes and requested language be added to page. KS has sent to development for deployment and asked Valerie for language they would like added. Language request is below: You can also find these forms from your home profile screen following these steps 1) On your employee home page click on your profile at the top left of the screen 2) Choose additional forms from the menu 3) Choose the forms or video you would like to review 9/2 - changes on HSPL copy have been moved to MATT Stage. | WT-610 |  | Development | 2016-09-02