## Pending Tasks
Priority | Task | JIRA | Status
V1 | Enforce Admin review to replace ISNULL function: - Email notification to employee on login and tour assignment will not be sent if the classes are all Null (this is only for those from API, not from Add Employee or Import/Export) - Email notification (daily) to admin on users without classes, reflecting count and redirecting to Admin Review page - Dashboard notification via widget to admin on users without classes, reflecting count and redirecting to Admin Review page - Create daily scheduler. Once classes are assigned, notification on login and tour assignment will be sent | NF-3053 | In Analysis
V1 | Aurico Integration- -Move the Aurico account configuration [client credentials, packageID, customer ID, contact person] at company level since this configuration will be separate for each company. [Currently we have this at config level which applies across the board i.e- same credentials for any company ] | NF-3054 | Dev Backlog
V1 | Aurico Integration- Drive menu navigation for “Employee Background Check” according to criteria of module selection. Currently this is driven only from Menu Action Enable / Disable- we should make this as a feature that can be switched ON / OFF by admin / partner. | NF-3055 | Dev Backlog
V1 | JWT audience update on CB routing layer- Change : CB authorization team is changing the audience field in the JWT exchnaged on the routing layer to be an array of strings instead of a single string. We need to update our JWT verification inorder to accommodate this. | NF-3070 | Dev Backlog
V2 | Admin Review - Additional Fields (eg: Wellness code) tied to plan and rate eligibility - Notification / widget on Admin dashboard for updating these fields | NF-2310 | On hold for now
V2 | Full OneIAM implementation - OneIAM AUthentication - Custom login - there are some regular customer too - Custom URL – only white label | NF-2306 | On hold for now
V2 | • Candidate level o Formal application letter o Offer letter o And anything else on candidate |  | To be discussed and scoped
V2 | Headers merge / integration with CB |  | To be discussed and scoped
V2 | Rehire scenario for employee records getting added via API call |  | Design / Analysis to be done with Onboard design for rehire
V2 | More fields (from TSR and BH) o Resume o List out fields from TSR and BH (placement data; job location etc) o Standard vs configurable fields |  | To be discussed and scoped: - Additional/Optional fields for API that can be pulled from Bullhorn - Getting resume and other fields from TSR
V2 | Aurico integration o Integration on a common service account (unlimited calls); options or packages are coming from 1 general account (not client specific) o Move it into integration framework o Check with Aurico team if it can be turned on for SPG |  | Nagini to check woth Aurico team - if we can go live for SPG with current setup. On low priority for now
V2 | Bullhorn integration - Update employee data for start date / demographics to be handled |  | Pending, Not to start as of now

## Dev estimates for NF-3053
Dev tasks to enforce Admin review to replace ISNULL function |  |  | Discussion Notes | Clarifications
Task Description | Implementation approach | Dev Efforts
Hold email notification containing Login credentials and tour notification [Only for employees added from API call if all classes are NULL] | Currently Email category for Add employee gets trigerred as soon as employee record is added in system. We need to add this additional check in add employee routines & send notification logic to hold this email if all of classes for employee are without any valid values. This same criteria in code will need to be applied for tour assignment via API call in order to hold tour notification email Note: Here, we will suggest not to hold the login email. Onboard team is currently adding check on tour start on basis of new hire mode window. In same logic we can add a condition to show eligible tour to employee only if all class information is set in system. This way even if employee logs in to system he / she will be either redirected to dahboard OR on generic welcome page [ as per system behaviour ]. And once admin sets the classes information- a notification for tour becoming eligible will be triggerred to this employee. Please let me know your thoughts on this. | Hold login credentials from API - Add employee Hold tour assignment notification from API - add employee routines Hold tour assignment notification from Manage onboard status page Unit Testing, Analysis, Discussion, Review, Code merge / checkin Total: 4 days | Not going with the non-holding of login email l since there are few actions users can take now on site without class (tour and enrollment dependent on class) | The 4 days does not include the original suggestion of not holding login email yes?
Create daily scheduler. Once classes are assigned, notification on login and tour assignment will be sent | Approach 1: Trigger email notification for tour assignment as soon as classes assignment is done. | Check if Tour assignment email category can be used Add placeholders on email message (if required) Logic to trigger notification on admin review page Unit Testing, Analysis, Discussion, Review, Code merge / checkin Total: 3 days | Not going with the immediate notification because scheduled email allow for consolidation of users added within the day
| Approach 2: Create a scheduler service [running at regular interval - suggested once everyday ] to scan for all companies and send tour eligibility notification to employees. This will aslo ensure that any tour becoming eligibile for employee due to some other data chnage is also considered while noifying employees of eligible tours. | Check if Tour assignment email category can be used Add placeholders on email message (if required) Create service scheduler to send notification Logic to scan system and trigger emails Unit Testing, Analysis, Discussion, Review, Code merge / checkin Total: 7.5 days | Shifting this task up before widget and emp notification so we don't hold UAT. | We should leverage on tour assignment email category (content looks relevant). For the eligibility from data change, is this part of the 7.5 days? Does this include the eligibility from mode?
Email notification to admin users for users without classes in system | Approach 1: Trigger email notification to Admin user as soon as employee record is added in system from API call. Define new email message category. Admin users to be included in this email will be a part of customization from screen. | Define new email category Add placeholders from email category Send notification to admin user on employee add from API Unit Testing, Analysis, Discussion, Review, Code merge / checkin Total: 4 days | Not going with the immediate notification because (1) the daily scheduler can also be extended for users newly eligible because of mode (2) classes may not be assigned in one shot and may affect eligibility
| Approach 2: Create a scheduler service to scan entire system [at regular interval - once everyday] for such employees with no class information and send a consolidated email for each company's respective admin user. Define new email message category. Admin users to be included in this email will be a part of customization from screen. | Define new email category Add placeholders from email category Create service scheduler to send notification Logic to scan system and trigger emails Unit Testing, Analysis, Discussion, Review, Code merge / checkin Total: 8 days | Not going with the specifiying of admin for the email because (1) the need is not validated (2) the proposition of utilising CC/BCC is not intuitive Saurabh will be sending proposed category and email content (with placeholders). Team can discuss if come up with other approach to admin assignment.
Dashboard notification via widget to admin on users without classes, reflecting count and redirecting to admin Review page | This will be done on new UI. A new counter will be placed on admin dashboard displaying the count of employees that do not have classes tied to them. Link this counter to Admin review page in system. | Add new counter on Admin dashboard Add link to assign classes payroll page Logic to get count of employees Unit Testing, Analysis, Discussion, Review, Code merge / checkin Total: 3.5 days |  | I believe the page can only satisfy max of 4 counters. Can please check if there are priority we can set that affects the order? If so, this should always listed before module specific counters e.g. Pending EOI. If none, we can leave it.
Note on F6: Tour Assignment Email: Dear [EmployeeName], You have been assigned the [TourName] tour for job position [JobPosition]. You are requested to take this tour and complete all the steps by [TourEndDate]. Please click here to get started. In case you have any questions while taking the tour, please contact the admin. Thank You, Admin Team Please note: This is an auto generated mail, kindly do not reply to this mail.