## Client Sign-off
	CLIENT	Fairleigh Dickinson University
	OnlinEnroll Acct. Mgr	Robyn Adkison / Ryan Sapp

Your OnlinEnroll Account Manager requests your participation in User Acceptance Testing (UAT). It is essential that these tests are performed to ensure the accuracy of your eligibility rules, benefit data and any other site customizations. / • The UAT instructions provide a thorough review of test scenarios that you should perform prior to going live with the application. / • Signing off on this UAT form means you have reviewed and tested the application based on the test categories identified in the UAT Instructions and are ready to go live with OnlinEnroll. / • This User Acceptance Testing form must be completed, signed, faxed/emailed to the OnlinEnroll Account Manager prior to going live. If the form is not received, go live can be postponed.

#	Activity	Responsibilities	Client Contact Providing Sign-off	Client Sign-off Date
Implementation Preparation
1	Milestones	Client	Rose D'ambrosio	06/03/2013
Information Gathering
2	Info Gathering Customer Questionnaire	Client	Stefanie Miller	09/11/2013
3	BOSS - Appendix A - C	Client	Stefanie Miller	08/12/2013
4	BOSS - Appendix D - K	Client	Stefanie Miller	08/06/2013
Build - Customer User Acceptance Testing (UAT) - see UAT Instructions for items requiring test to provide final approval on below
5	UAT Employee Scenario Testing and Client sign-off of build	Client	Stefanie Miller	10/23/2013
6	UAT Review & Sign-off of Employee, Dependent Child & Spouse Demographic and Enrollment Data	Client	Stefanie Miller	10/23/2013

Accepted: My signature below indicates that I have completed testing and agree the site is ready to Go Live.

	Wet Signature		Date

	Print Name, Title and Organization

## UAT Instructions
PART ONE - UAT Employee Scenario Testing and Client Sign-Off of Build
Test employees will be provided to you by your OnlinEnroll Account Manager to ensure the appropriate number of test scenarios are completed. These test employees should be used to thoroughly vet site build accuracy based on the specifications you provided.
Pre-Enrollment Validation Checklist
Pages To Review		Components Requiring Validation	Approve (Yes/No)	Findings (identify plan name(s) and errors, if any)
Company Logo		- Logo appearance
Employee Usage Agreement & Legal Agreement		- Custom Text
Landing Pages for the following: / - Open Enrollment / - New HireLanding Pages for the following: / - Open Enrollment / - New Hire		- Custom Text
Demographic Pages for the following: / - Employee / - Spouse / - ChildDemographic Pages for the following: / - Employee / - Spouse / - Child		- Custom Text / - Info fields are displaying accurately / - Permissions are correct for all fields- Custom Text / - Info fields are displaying accurately / - Permissions are correct for all fields
Emergency Contact Page		- Custom Text / - Info fields are displaying accurately / - Permissions are correct for all fields- Custom Text / - Info fields are displaying accurately / - Permissions are correct for all fields
Custom Form(s) / (e.g. EE Acknowledgement.)Custom Form(s) / (e.g. EE Acknowledgement.)		- Custom Text / - Appropriate user selections/values / - Alignment to employees or enrollment- Custom Text / - Appropriate user selections/values / - Alignment to employees or enrollment
Enrollment Pages Validation Checklist
Items Requiring Validation	Frequency of Validation	Components Requiring Validation of Item	Approve (Yes/No)	Findings (identify plan name(s) and errors, if any)
Plan Eligibility	Per Employee Group/Class, Per Plan & Per Plan Enrollment Page	- Accuracy of plans available for election based on specifications provided / - Dependent types available to enroll (e.g. Spouse, Domestic Partner, Child) / - Employee enrollment permissions (e.g. Plans are viewable but not editable) / - Waiver message or reasons appears on plans (if applicable)- Accuracy of plans available for election based on specifications provided / - Dependent types available to enroll (e.g. Spouse, Domestic Partner, Child) / - Employee enrollment permissions (e.g. Plans are viewable but not editable) / - Waiver message or reasons appears on plans (if applicable)
Effective Date	Per Plan & Employee Group/Class	- Accuracy of plan effective dates based on waiting period rules and date of hire
Coverage Amounts	Per Plan, Tier, Age or Employee Group/Class	- Available coverage values displaying/calculating correctly / - Covered GI amounts / - Maximums and Minimums are being applied correctly / - Age Reductions are calculating correctly- Available coverage values displaying/calculating correctly / - Covered GI amounts / - Maximums and Minimums are being applied correctly / - Age Reductions are calculating correctly
Plan Contingency(s)	Per Plan & Employee Group/Class	- Plans only show if meet criteria (e.g. elected Medical, has dependent) / - Tier or Coverage restrictions work- Plans only show if meet criteria (e.g. elected Medical, has dependent) / - Tier or Coverage restrictions work
Rates	Per Plan, Tier, Age, Pay Frequency or Employee Group/Class	- Display of contribution types (EE & ER) / - Accurate pre/post tax identifier / - Tiered rates / - Additional Discounts & Surcharges applying as should (e.g. spousal surcharge, tobacco user, wellness credit) / - Coverage based rate calculations / - Age Bands & Age Reductions are calculating rate correctly / - Maximums and Minimums are being applied correctly / - Converting yearly contributions to per-pay-period (e.g. HSA, FSA)
Custom Text, Documents and Links / - Header Page Text / - Forms Library / - Learn about your Benefits / - Benefit Descriptions / - Pop ups (e.g. EOI Forms, plan info)	Per Plan Enrollment Page	- Custom Text / - Any external website links work / - All documents & forms provided for storage are available in proper location for review/display/print by employee
Post Enrollment Validation Checklist
Pages To Review		Components Requiring Validation	Approve (Yes/No)	Findings (identify plan name(s) and errors, if any)
Beneficiary Page		- Custom Text
Confirmation Statement		- Custom Text / - Sections for Display (e.g. Beneficiaries, Emergency Contact) / - Employee/Employer Cost is displaying as should
Election Confirmation Pop-up / - Open Enrollment / - New Hire		- Custom Text

PART TWO - Sign-off of Employee, Dependent Child & Spouse Demographic and Enrollment Data
Your OnlinEnroll Account Manager will provide training on the reporting features in the site to ensure that you can validate the census and enrollment information loaded is in line with the data provided.
Items Requiring Validation in Site:			Approve (Yes/No)	Findings (identify plan name(s) and errors, if any)
Run Employee Census report and validate that all employees are accounted for and accurate
Run Dependent census report and validate all dependents are accounted for and accurate
Run enrollment reports to include employee, dependents, enrollment and coverage information and confirm benefit enrollment, effective dates and rates

## Client Info Sheet
last updated: 01/09/17
Client Name:	Fairleigh Dickinson University		Site Name:	FDU			Test HR Admin
Account Manager:	Robyn Adkison					User Name	Password
					FDUAdmin	FDUPass@1!

Class Name(s)	Value Name(s)				Please provide reason why the classes are broken out
Class 1	Union Staff, Non-Union Staff, Faculty, Part Time Ineligible				Medical Plan and rates / Note: Faculty is eligible for the non union medical
Class 2	FDU, Test

Company Rules					Connections		Frequency & Day
New Hire/Rehire Waiting Period	Enrollment Window	Termination Rule			UHC Medical		Weekly, Friday
					UHC FSA		Weekly, Friday
Date of hire	31 days from date of hire	Term at the end of the month			UHC COBRA		Weekly, Friday
					Delta Dental		Weekly, Friday
					MetLaw		Monthly first of month / *Note: There is also a global template "FDU MetLaw PreRun" that the CE will need to manually set the schedule for every year for the last day of every month
					ADP Payforce		TBD
					AIS		TBD
Payroll Schedule Setup		Classes
Semi-Monthly (9 months - 18 pay dates)		all			Internal OnlinEnroll Use Only
Semi-Monthly (10 months - 20 pay dates)		all			Which Health Tier Label Set was used?
Semi Monthly (11 months - 22 pay dates)		all - Note: there are 2 SM 11 calendars set up. the one with a dash is old and should not be used			Domestic Partner with Standalone DP Children
Semi-Monthly		all			Custom Fields (Demographics)
					- Grandfathered for Life Benefits - Drives Grandfathered Plans / - Campus - used for reporting purposes / - Does the EE need to review the FDU Ack. Page? - used to drive the acknowledgement page for new hires / - COBRA bill suspension - Used to place an indicator on the COBRA file to delay billing for those termed in May / -TIAA CREF ER match % - Not used / -ETG Award 2012 2013 - Not used / -Acknowledgement page - used to view the form for new hires
					Custom Forms
					- Dependent warning - Standard / - FDU Acknowledgment Page - New Hires only / - HSA Affidavit / -Tenure - Pending FDU review (not built yet)

List all Qualifying Events that are setup		List any changes from default settings			List QE Effective Date & Retro Days		Indicate if Event Builder is setup for QE & rules for
		(e.g. verification type, event rule, future days, plan/demographic restrictions)
Admin Event		90 Future			Event Date / 550		No
Birth or Adoption or Placement for Adoption		No Vision Plan			Event Date / 31
Commencement of Same Sex Domestic Partner		No Vision Plan			Event Date / 31				Inactive 7/3/17
Court Order (Qualified Medical Child Supp Order)		No Vision Plan / Event allows Only Increase in Coverage			Event Date / 31
Death of Spouse or Child		No Vision Plan			Event Date / 31
Dependent Demographic Information Change		No Vision Plan / Event allows no enrollment action			Event Date / 31
Dissolution of Same Sex Domestic Partner		No Vision Plan			FOM foll Event (not coin.) / 31
Divorce Employee Enrolling in FDU Coverage		No Vision Plan			Event Date / 31				Inactive 7/3/17
Divorce Spousal Loss of Coverage		No Vision Plan			FOM foll Event (not coin.) / 31
Emp Out of Work Due to Strike or Lockout		No Vision Plan			FOM foll Event (not coin.) / 31
Emp Returns to Work After Strike or Lockout		No Vision Plan / Event allows Only Increase in Coverage			Event Date / 31
Employee or Dependent Gains Coverage Elsewhere		60 Future/ No Vision Plan			Event Date / 31
Employee or Dependent Loses Other Coverage		60 Future/ No Vision Plan			Event Date / 31
End of Your Spouse FMLA Leave		No Vision Plan			Event Date / 31
Legal Guardianship		No Vision Plan / Event allows Only Increase in Coverage			Event Date / 31
Marriage		No Vision Plan			Event Date / 31
Start of Your Spouse FMLA Leave		No Vision Plan / Event allows Only Increase in Coverage			Event Date / 31
HSA Contribution changes		Only for HSA contribution plans. - Rules TBD			FOM foll Event /0
Plan Eligibility due to Class Change		No Vision Plan			FOM foll 30 days / 31		Yes - activated when Ees move from part time inactive to any other class 1		not currently used. - Set up for future AIS purposes

Brief Summary of Plan - List all plans that need to be built (can combine plans if all rules are same), only complete applicable components for plan
Carrier		UHC/Delta	UHC/Delta	UHC/Delta	UHC	UHC	UHC	UHC	The Guardian	The Guardian	The Guardian	The Guardian	The Guardian	The Guardian	The Guardian	The Guardian	MetLife	Unum	Premier Option
Plan Name		POS Medical/ Dental	CDHP Medical/Dental	Waive Medical and Dental Plan	Healthcare Savings Account	2017 Healthcare Savings Account Catch Up	FSA	DFSA	Basic Life & AD&D	STD	LTD	Supplemental Life	Supplemental AD&D	Supplemental Spouse Life	Supplemental Spouse AD&D	Grandfathered Supplemental Life	Grandfathered Supplemental AD&D	Grandfathered Supplemental Spouse Life	Grandfathered Supplemental Spouse AD&D	Supplemental Child Life	Supplemental ChildAD&D	MetLaw	LTC	Vision
Unique Elig Rules		Dental enrollment is bundled with Medical					- Grandfather = No	- Grandfather = No	- Has spouse = Yes / - Grandfather = No	- Has spouse = Yes / - Grandfather = No	Custom field: Grandfathered for Life benefits = Yes					Benefit coverage and cost will be uploaded by FDU / Using user defined benefit. Benefit cost and coverage will be updated by FDU	Post link to enrollment form. No enrollment in site.
Rate Surcharges/Discounts		- Sliding scale for salaries with single coverage / - union with ee + dependents under lower end of ss receive a 700 or 1000 credit, / - EE's under ss with EE only coverage is $0 / --Sliding Scale -- / 2013: 31310 - 38496 / 2014: 31623 - 38881 / 2015: 32730 - 40242 / 2016: 33385 - 41047 / 2017: 33719 - 41457
Contingencies					EE Sup Life		SP Life		Grandfathered EE Sup Life		Grandfathered SP Life	EE Sup Life	CH Life
Proof of Other Coverage Req'd		Yes, must show proof of current insurance for medical only
Plan Defaults		Defaults to the medical waiver Plan
Auto-Enroll					yes					elected amount		elected amount
Auto-Enroll/Voluntary Coverage Amounts					1x annual Salary - 50k max	2/3 of weekly salary	60% of monthly salary	10k - 500k incre 10K	100% of EE Supplemental Life	10k - 250k incre 10k	100% of SP Supplemental Life					10000	10000					EE Life	250,000	SP Life	120,000	based on current site design - it is cutting ee coverage in half and then providing reduced values to that amount - in this example highest value in site is $52k
GI					140k / (if over 65, 10k / if over 70 all GI, will need to be client monitored)		20k					EOI is required for late entrants only (10,000 for nh/rh and 0 for all others)					Expected amount
Plan Max/Min					Single 3400 / Family 6750 / min 0 / over 55 additional $1,000	$1000/0	2600/25	5000/25	max 50k	up to weekly state max (will change yearly) / 2014: 595 / 2015: 604 / 2016: 615 / 2017: 633	15,000 per month	500k/10k	match EE Supp life	250k/10k / can not exceed 50% of EE Sup Life	match SP life	$500k/$1	$500k/$1	$250k/$1	$250k/$1	flat 10,000	flat 10,000					65	162,500	65	78,000
Other					ER contribution Prorated Quarterly: / $500 Single / $1,000 Family					EE only plan
Plan Specific Reduction &/or Rounding Rules					round to next higher 1k	Rounded to the next lower 1.00 if not already a multiple of 1.00	rounded to nearest $1.00	65 - reduce 35%, rounded to next higher 500, but no less than 1k. / 80- additional 25% rounded to next higher mult of 500, no less than 1k	age 100/100% - coverage should match EE life, when reduction happens on EE life, EE ad&d will match that	65 - reduce 35%, rounded to next higher 500, but no less than 1k. / 80- additional 25% rounded to next higher mult of 500, no less than 1k	age 100/100% - coverage should match spouse life, when reduction happens on sp life, sp ad&d will match that
List any Plan Specific Waiting Period, Salary & Age Change, or Term Rules		- Pend plan for HR as FDU wants to reviw all dep prior to benefits / - Salary changes that affect benefit should be effective on the date of change / - Efft. FOM foll or coin. With 30 days from DOH		- built to accommodate the payroll file. / - Only available to the EE / - Efft. FOM foll or coin. With 30 days from DOH	Terms on date of Term / - Allowed to waived or enter $0	Terms on date of term	- Benefit terms on date of termination / - Efft. FOM foll or coin. With 30 days from DOH		- Benefit terms on date of termination / -coverage updates first of the month following or coincident after salary change / - Efft. FOM foll or coin. With 30 days from DOH	- Benefit terms on date of termination / -coverage updates first of the month following or coincident after salary change	- Benefit terms on date of termination / -coverage updates first of the month following or coincident after salary change / - Efft. FOM foll or coin. With 30 days from DOH	cov updates jan1 after they enter a new a new age bracket . i.e. member turns 50 this year, will pay new rate jan 1 of next year. / - New hire's/mid year changes for rates for age banded plans use the age of the EE as of 1/1 of current year / - Efft. FOM foll or coin. With 30 days from DOH		cov updates jan1 after they enter a new a new age bracket . i.e. member turns 50 this year, will pay new rate jan 1 of next year. (note spouse life is based on ee age) / - New hire's/mid year changes for rates for age banded plans use the age of the EE as of 1/1 of current year / - Efft. FOM foll or coin. With 30 days from DOH		All age and salary rules follow the regular life and AD&D plans. However, these grandfathered plans will need to be adjusted manually every year. these plans were built as "user defined" to accommodate members whose plans did not conform to the plan rules. No new members should be entered. / 2015 update: due to system limitations, When a member turns 65 and is now subject to the age reduction, if they have spouse life, the member will need to be moved to the grandfathered life plan, as the spouse life plan cannot calculate the reduction properly				- Efft. FOM foll or coin. With 30 days from DOH	- Efft. FOM foll or coin. With 30 days from DOH	Ees need to re elect this plan every year. Plan will need to be rebuilt every year

Carrier & Plan Name	Brief Summary of Plan				List any Plan Specific Reduction &/or Rounding Rules		List any Plan Specific Waiting Period, Salary & Age Change, or Term Rules
List all that need to be built	Include if any: Unique Elig Rules, Rate Surcharges/Discounts, Contingencies, Proof of Other Coverage Req'd, Plan Defaults, Auto-Enroll, Auto-Enroll/Voluntary Coverage Amounts, GI, Plan Max/Min