## Production to Stage
Company Move Checklist - Production To Stage
Company Name		Affco
JIRA ID		WT-11356
Environment Tested		Stage
Date		16/10/2017

Sr. No.	Functionality	Status	JIRA ID	Remark
1	JIRA - Read and Understand. Discuss if any queries / Identify the action items for Employee, Partner and Admin level.JIRA - Read and Understand. Discuss if any queries	Done
2	Observe the Company Name given in JIRA comments	Done
	Login with Partner
3	Check for Company Access to Partner User, If access is not available then get it from Ashwin/Khandu/Leads	Done
4	Go to 'Site Branding and Themes' page and save the theme which is already applied. / NOTE : ( Do not chagne the theme until its mentioned explicitly)Go to 'Site Branding and Themes' page and save the theme which is already applied.	Done
5	Go to Company Information tab and Save the Information page / NOTE : ( Confirm the Company Name displayed in Company Name field is same as mentioned in JIRA)Go to Company Information tab and Save the Information page	Done
6	Verify all tab under Company information
7	Go to Company Module Mapping and click on Update button to save the mapped module(s).	Done
8	Go to 'Employee Data Screen' tab and click on Save button to save the EDS.	Done
9	Configure Tiles, widgets, counter on Home page of company.	Done
10	Add New Employee / NOTE : ( Note the Employee Details like Name, Username,Password for further use and deletion purpose)Add New Employee	Done
	Login with Employee
11	Check if employee gets Self Serve Mode to traverse.(Verified qualifying event workflow)	Pass
12	Employee Usage Agreement	Pass
13	Legal Agreement	Pass
14	landing Page	Pass
15	Change Password Page	Pass
16	Demographics	Pass
17	Spouse	Pass
18	Child	Pass
19	Upload document
20	Enroll Now-Medical	Pass
21	Enroll Now-Dental	Pass
22	Enroll Now-Vision	Pass
23	Enroll Now-Hourly Basic Life	Pass
24	Enroll Now-Hourly Basic AD&D	Pass
25	Enroll Now-Supplemental Employee Life	Pass
26	Enroll Now-Supplemental Employee AD&D	Pass
27	Enroll Now-Short Term Disability	Pass
28	Enroll Now-Long Term Disability	Pass
29	Enroll Now-GAP	Pass
30	Enroll Now-Long Term Disability	Pass
31	Beneficiary	Pass
32	Confirmation Statement	Pass
	Login with Partner
33	Partner Login>Reports	Pass
34	Standard Report-Verified Run,Excel,PDF, HTML,schedule,clone functionality	Pass
35	Dynamic Report	Pass
36	Static report->Student Status Verification Report	Pass
37	Static report->Confirmation Statement Report	Pass
38	Static report-> Mail Merge Report	Pass
39	Static report->Employee Plan Eligibility Report	Pass
40	Static report-> Cobra Term Report	Pass
41	Static report->Qualifying Event Report	Pass
42	Static report-> Rejection Report	Fail	WT-11389
43	Static report->Admin Enrollment Report	Fail	WT-11389
44	Static report->Billing Summary Report	Pass
45	Static report-> Age Report	Pass
46	Static report->Court Ordered Dependent Coverage Report	Pass
47	Static report-> Dependent Overage Report	Pass
48	Static report-> Add Change Term Report	Pass
49	Static report-> Plan Design Summary Report	Pass
50	Static report->Commission Report	Pass
51	Static report-> Rates Report	Pass
52	Static report->Employee TimeSheet Discrepancy Report	Pass
53	Static report-> Paper Enrollment	Pass
54	Static report->IRS Submission	Pass
55	Static report-> Employee Upload Document Report	Pass
56	Open Enrollment Changes Report	Pass
57	New Enrolled Dependents Report	Pass
58	Invoice Management	Pass
59	View Finalized Invoices	Pass
60	Discrepancy Report	Pass
61	Partner Login>Navigate different links under “Customizer" tab	Pass
62	Customizer->Classes	Pass
63	Customizer->Benefit Type->Verified Benefit type name and supplemental employee AD &D	Pass
64	Customizer-> Generic Eligibility Rules	Pass
65	Customizer-> Zip Tables	Pass
66	Customizer->Credit Pool	Pass
67	Customizer-> Default Plan Mappping	Pass
68	Customizer->Rate Plan Design Mapping	Pass
69	Customizer-> Benefit Description Plan Design Mapping	Pass
70	Customizer->Plan Design Health Tier Mapping	Pass
71	Customizer-> Benefit Provider	Pass
72	Customizer->Benefit Description	Pass
73	Customizer->Health Tier Labels	Pass
74	Customizer-> Qualifying Event Details	Pass
75	Customizer-> Format Total Compensation Statement	Pass
76	Customizer->Waiver Reasons	Pass
77	Customizer-> Format Confirmation Statement	Pass
78	Customizer->Plan Comparison Builder	Pass
79	Customizer-> Reorder Benefit Types	Pass
80	Customizer->Reorder Plan Designs	Pass
81	Customizer-> Upload EOI Forms	Pass
82	Customizer->Event Builder	Pass
83	Customizer-> Format Paycheck	Pass
84	Customizer->Summary of Benefits and Coverage (SBC)	Pass
85	Customizer->Form Builder	Pass
86	Customizer->Configure Change Approval	Pass
87	Customizer->Configure Landing Page	Pass
88	Customizer->Configure Employee Popup	Pass
89	Customizer-> Configure Search Employee	Pass
90	Customizer->Forms Library	Pass
91	Customizer-> Video/Brochure Library	Pass
92	Customizer-> Admin Users	Pass
93	Customizer->Security	Pass
94	Customizer->Themes & Site Branding	Pass
95	Customizer-> Site Branding & Configuration	Pass
96	Customizer-> Notes Categories	Pass
97	Customizer->Upload Images	Pass
98	Customizer-> Question Plan Mapping	Pass
99	Customizer->Rates	Pass
100	Partner Login>Navigate different links under "Employer Administration" tab	Pass
101	Company information	Pass
102	Verified Payroll Schedule page	Pass
103	Verified Paid Time Off page	Pass
104	Verified View History	Pass
105	Verified Incomplete Enrollment Notification	Pass
106	Verified Incomplete Enrollment Notification - Benefit Wise	Fail	WT-11231
107	Verified Qualifying Event Email Notification	Pass
108	Partner Login>Navigate different links under "Employee Administration" tab	Pass
109	Verified add employee page	Pass
110	Verified search employee page	Pass
111	Verified Assign Classes and Payroll Schedule page	Pass
112	Verified review changes page	Pass
113	Verified Pending EOI page	Pass
114	Verified Review Dependent Audit page	Pass
115	Verified Pending Queue page	Pass
116	Verified Review Employee Document page	Pass
117	Partner Login>Navigate different links under "Import/Export" tab	Pass
118	Verified manual Import /Export page	Pass
119	Verified Template management page	Fail	WT-11626
120	Verified View Bad File page	Pass
121	Verified View Calendar page	Pass
122	Verified View Exported Files page	Pass
123	Verified Open Enrollment Setting page	Pass
124	Verified Upload PGP Key page	Pass
125	Partner Login>Navigate different links under "Communication" tab	Pass
126	Verified E-mail Broadcast page	Pass
127	Verified E-mail Message Format page	Pass
128	Verified Schedule Notification page	Pass
Employee level
129	Search for employee	Pass
130	Manage Employee by partner	Pass
131	Employee->Profile	Pass
132	Employee->Demographics	Pass
133	Employee->Organization Chart	Pass
134	Employee->Education Information	Pass
135	Employee-> Emergency Contact	Pass
136	Employee->Primary Care Provider	Pass
137	Employee-> Underwriting	Pass
138	Employee-> Employment Management	Pass
139	Employee->Change Classes	Pass
140	Employee-> Compensation History	Pass
141	Employee->Change status	Pass
142	Employee->Change Password	Pass
143	Employee-> Initiate Qualifying Events	Pass
144	Employee-> Forms Library	Pass
145	Employee->Notes	Pass
146	Employee-> View History	Pass
147	Employee->Upload Documents	Pass
148	Employee->Additional form->Special Classification	Pass
149	Dependents-> Child	Pass
150	Dependents->Spouse	Pass
151	Dependents->Terminate dependent benefits	Pass
152	Benefits->Enroll Now	Pass
153	Benefits->Terminate plan Elections	Pass
154	Benefits->Medicare	Pass
155	Benefits->Medicaid	Pass
156	Benefits-> Beneficary	Pass
157	Benefits->Coordination of Benefits	Pass
158	Benefits-> Proof of other coverage	Pass
159	Benefits->Total Compensation Statement	Pass
160	Benefits-> View Paycheck	Pass
161	Benefits->Confirmation Statement	Pass
162	Benefits-> Plan Comparison Tool	Pass
163	Benefits->Enrollment Summary	Pass
164	Benefits->Terminate as never effective	Pass
165	Reports->Eligibility Report	Pass
166	Reports->Enrollment Report	Pass
167	Reports-> Enrollment History Report	Pass
168	Reports->Employee Plan Eligibility Report	Pass
169	Reports->Beneficiary Report	Pass
170	Reports-> Employee Timesheet Report	Pass
171	Reports->1095-C	Pass