## Stage to Production
Company Move Checklist - Stage to Production
Company Name		AFFCO		Company Name		AFFCO For HSPL
JIRA ID		WT-11779		JIRA ID		WT-11779
Environment Tested		Stage		Environment Tested		Production
Date		25/10/2017		Date		25/10/2017

Sr. No.	Functionality	Status		Sr. No.	Functionality	Status	JIRA ID	Remark
1	JIRA - Read and Understand. / Discuss if any queries. / Identify the action items for Employee, Partner and Admin level.	Done		1	JIRA - Read and Understand. / Discuss if any queries. / Identify the action items for Employee, Partner and Admin level.	Done
2	Observe the Company Name given in JIRA comments	Done		2	Observe the Company Name given in JIRA comments	Done
					Create the HSPL copy on production and do test execution on HSPL Copy only.
	STAGE				PRODUCTION
	Login with Partner on Stage and Production simultaneously and start comparative testing
3	Check for Company Access to Partner User, If access is not available then get it from Ashwin/Khandu/Leads	Done		3	Check for Company Access to Partner User, If access is not available then get it from Ashwin/Khandu/Leads	Done
4	Go to 'Site Branding and Themes' page	Pass		4	Go to 'Site Branding and Themes' page. / - Compare and Apply the theme as on stage / Go to 'Site Branding and Themes' page.	Pass
	NOTE : (Do not chagne the theme until its mentioned explicitly)
5	Go to Company Information tab	Pass		5	Go to Company Information tab / - Compare the Company Information Tab details and Save the Information page.	Pass
	NOTE : ( Confirm the Company Name displayed in Company Name field is same as mentioned in JIRA)
6	Go to Company Contact Information tab	Pass		6	Go to Contact Information tab / - Compare the Contact Information tab details with Stage. / Go to Contact Information tab	Pass
7	Go to System Settings tab	Pass		7	Go to System Settings tab / - Compare the System Settings tab details with Stage. / Go to System Settings tab	Pass
8	Go to Company Classes tab	Pass		8	Go to Company Classes tab / - Compare the Company Classes tab details with Stage. / Go to Company Classes tab	Pass
9	Go to Company Module Mapping tab	Pass		9	Go to Company Module Mapping tab / - Compare and map the Module as on stage then click on Update button to save the mapped module(s).	Pass
10	Go to New Hire/Rehire Rule tab	Pass		10	Go to New Hire/Rehire Rule tab / - Compare the New Hire/Rehire Rules and eligibility settings. / Go to New Hire/Rehire Rule tab	Pass
11	Go to Effective Date/Termination Date Rule tab	Pass		11	Go to Effective Date/Termination Date Rule tab / - Compare the Effective Date/Termination Date Rules and eligibility settings. / Go to Effective Date/Termination Date Rule tab	Pass
12	Go to 'Employee Data Screen' tab	Pass		12	Go to 'Employee Data Screen' tab / - Comapre with Stage and click on Save button to save the EDS. / Go to 'Employee Data Screen' tab	Pass
13	Customizer > Security	Pass		13	Customizer > Security / - Compare Security Page settings with Stage / Customizer > Security	Pass
14	Customizer > Dashboard Configuration			14	Customizer > Dashboard Configuration / - Compare and Configure the Dashboard settings as that are on Stage / Customizer > Dashboard Configuration
15	Customizer > Rates	Pass		15	Customizer > Rates / - Compare the Rates on Stage / Customizer > Rates	Pass
16	Customizer > Benefits Library > Add/Change Plan Design	Pass		16	Customizer > Benefits Library > Add/Change Plan Design / - Compare the Plans,Count,Logs under each Benefit Type on Stage	Pass
17	Customizer > Site Branding and Configurations	Pass		17	Customizer > Site Branding and Configurations / - Compare settings with Stage / Customizer > Site Branding and Configurations	Pass
18	Customizer > Employee Screen Configuration > Configure Landing Page	Pass		18	Customizer > Employee Screen Configuration > Configure Landing Page / - Compare the Landing page Count, Text and Settings	Pass
19	Employer Information > Payroll schedules	Pass		19	Employer Information > Payroll schedules / - Comare the Payroll Schdules with Stage / Employer Information > Payroll schedules	Pass
20	Forms Library / - Check if all the files / forms are down loaded	Pass		20	Forms Library / - Check if all the files / forms are down loaded	Pass
	NOTE : ( Note the Employee Details like Name, Username,Password for further use and deletion purpose.) / To do an efficient comparative testing its recommanded that Employee Data should be exactly same on Stage and Prodution. / NOTE : ( Note the Employee Details like Name, Username,Password for further use and deletion purpose.) / To do an efficient comparative testing its recommanded that Employee Data should be exactly same on Stage and Prodution. / NOTE : ( Note the Employee Details like Name, Username,Password for further use and deletion purpose.) / To do an efficient comparative testing its recommanded that Employee Data should be exactly same on Stage and Prodution. / NOTE : ( Note the Employee Details like Name, Username,Password for further use and deletion purpose.) / To do an efficient comparative testing its recommanded that Employee Data should be exactly same on Stage and Prodution. / NOTE : ( Note the Employee Details like Name, Username,Password for further use and deletion purpose.) / To do an efficient comparative testing its recommanded that Employee Data should be exactly same on Stage and Prodution.
	Login with Employee on Stage and Production simultaneously and start comparative testing
21	Add new Employee / Check if employee gets Self Serve Mode to traverse.			21	Add new Employee / Check if employee gets Self Serve Mode to traverse.
22	Traverse the entire Self Serve Mode and list down the pages traversed			22	Traverse the entire Self Serve Mode and list down the pages traversed
	NOTE : (Compare the Paycheck Model, Forms Libray , Coverage amounts, Costs, Plan Names, Links, Logos, Alert Messages with Stage company )
	List of SSM Pages here				List of SSM Pages here
23	Employee Usage Agreement	Pass		23	Employee Usage Agreement	Pass
24	Legal agreement	Pass		24	Legal agreement	Pass
25	Landing page	Pass		25	Landing page	Pass
26	Change Password	Pass		26	Change Password	Pass
27	Demographics	Pass		27	Demographics	Pass
28	spouse	Pass		28	spouse	Pass
29	child	Pass		29	child	Pass
30	Enroll now- Medical	Pass		30	Enroll now- Medical	Pass
31	Enroll now- Dental	Pass		31	Enroll now- Dental	Pass
32	Enroll now- Vision	Pass		32	Enroll now- Vision	Pass
33	Enroll now- Basic Employee Life	Pass		33	Enroll now- Basic Employee Life	Pass
34	Enroll now-Basic Employee AD&D	Pass		34	Enroll now-Basic Employee AD&D	Pass
35	Enroll now-Supplemental Employee Life	Pass		35	Enroll now-Supplemental Employee Life	Pass
36	Enroll now-Short Term Disability	Pass		36	Enroll now-Short Term Disability	Pass
37	Enroll now- Long Term Disability	Pass		37	Enroll now- Long Term Disability	Pass
38	Enroll now- GAP	Pass		38	Enroll now- GAP	Pass
39	Beneficiary	Pass		39	Beneficiary	Pass
40	Upload document	Pass		40	Upload document	Pass
41	Confirmation statement	Pass		41	Confirmation statement	Pass
42				42
43	Employee > Enroll in some plans	Pass		43	Employee > Enroll in some plans	Pass
44	Employee > Waive some plans	Pass		44	Employee > Waive some plans	Pass
45	Employee > Add Spouse	Pass		45	Employee > Add Spouse	Pass
46	Employee > Add Child	Pass		46	Employee > Add Child	Pass
47	Employee > Add Beneficiary	Pass		47	Employee > Add Beneficiary	Pass
48	Employee > Change the Password	Pass		48	Employee > Change the Password	Pass
49	Employee > Confirmation Statement > Print and Download	Pass		49	Employee > Confirmation Statement > Print and Download	Pass
50	Employee Dashboard verification	Pass		50	Employee Dashboard verification	Pass
51	Navigate different menu's with employee login to check 'Server Error' is not displayed on click of any link.	Pass		51	Navigate different menu's with employee login to check 'Server Error' is not displayed on click of any link.	Pass
52	Verify Employee Reports	Pass		52	Verify Employee Reports	Pass
	Login with Partner on Stage and Production simultaneously and start comparative testing
53	Search for employee	Pass		53	Search for employee	Pass
54	Manage Employee by partner	Pass		54	Manage Employee by partner	Pass
55	Manage Employee by partner > Navigate different links when partner is managing employee (e.g. Medicare,Medicaid, Terminate as never effective, Coordination Benefits, Change Status, Primary Care Provider)	Pass		55	Manage Employee by partner > Navigate different links when partner is managing employee (e.g. Medicare,Medicaid, Terminate as never effective, Coordination Benefits, Change Status, Primary Care Provider)	Pass
56	Partner Login > Reports	Pass		56	Partner Login > Reports	Pass
57	Partner Login > Navigate different links under "Employee Administration" tab	Pass		57	Partner Login > Navigate different links under "Employee Administration" tab	Pass
58	Partner Login > Navigate different links under "Employer Administration" tab	Pass		58	Partner Login > Navigate different links under "Employer Administration" tab	Pass
59	Partner Login > Navigate different links under "Customizer" tab	Pass		59	Partner Login > Navigate different links under "Customizer" tab	Pass
60	Partner Login > Navigate different links under "Import/Export" tab	Pass		60	Partner Login > Navigate different links under "Import/Export" tab	Pass
61	Partner Login > Navigate different links under "Communication" tab	Pass		61	Partner Login > Navigate different links under "Communication" tab	Pass
	Login with Company Admin on Stage and Production simultaneously and start comparative testing
62	Customizer	Pass		62	Customizer	Pass
63	Employee Screen Configurations > / Configure Landing Page	Pass		63	Employee Screen Configurations > / Configure Landing Page	Pass
64	Employee Screen Configurations > / Configure Change Approval	Pass		64	Employee Screen Configurations > / Configure Change Approval Employee Screen Configurations > / Configure Change Approval Employee Screen Configurations > / Configure Change Approval	Pass
65	Forms Library	Pass		65	Forms Library	Pass
66	Video/ Brochure Library	Pass		66	Video/ Brochure Library	Pass
67	Admin Users	Pass		67	Admin Users	Pass
68	Change Password	Pass		68	Change Password	Pass
69	Upload Images	Pass		69	Upload Images	Pass
70	Security	Pass		70	Security	Pass
71	Notes Categories	Pass		71	Notes Categories	Pass
72	Site Branding and Configurations	Pass		72	Site Branding and Configurations	Pass
73	Employer Administration	Pass		73	Employer Administration	Pass
74	Company Information	Pass		74	Company Information	Pass
75	Incomplete Enrollment Notification	Pass		75	Incomplete Enrollment Notification	Pass
76	Incomplete Enrollment Notification - Benefit Wise	Pass		76	Incomplete Enrollment Notification - Benefit Wise	Pass
77	Event Notification	Pass		77	Event Notification	Pass
78	Employee Administration	Pass		78	Employee Administration	Pass
79	Add Employee	Pass		79	Add Employee	Pass
80	Search Employee	Pass		80	Search Employee	Pass
81	Review Changes	Pass		81	Review Changes	Pass
82	Pending EOI	Pass		82	Pending EOI	Pass
83	Review Dependant Audit	Pass		83	Review Dependant Audit	Pass
84	Pending Queue	Pass		84	Pending Queue	Pass
85	Review Employee Document	Pass		85	Review Employee Document	Pass
86	Reports	Pass		86	Reports	Pass
87	Discrepancy Report	Pass		87	Discrepancy Report	Pass
88	Billing Plan Code	Pass		88	Billing Plan Code	Pass
89	Import / Export	Pass		89	Import / Export	Pass
90	Template Management	Pass		90	Template Management	Pass
91	Upload PGP Key	Pass		91	Upload PGP Key	Pass
92	Search for employee	Pass		92	Search for employee	Pass
93	Manage Employee by Admin	Pass		93	Manage Employee by Admin	Pass
94	Manage Employee by Admin > Navigate different links when Admin is managing employee.	Pass		94	Manage Employee by Admin > Navigate different links when Admin is managing employee.	Pass