## Stage to Production
Company Move Checklist - Stage to Production
Company Name |  | Optimum | Company Name |  | Optimum for HSPL
JIRA ID |  | WT-11780 | JIRA ID |  | WT-11780
Environment Tested |  | Stage | Environment Tested |  | Prod
Date |  | 2017-10-25 | Date |  | 2017-10-25
Sr. No. | Functionality | Status | Sr. No. | Functionality | Status | JIRA ID | Remark
1 | JIRA - Read and Understand. Discuss if any queries. Identify the action items for Employee, Partner and Admin level. | Done | 1 | JIRA - Read and Understand. Discuss if any queries. Identify the action items for Employee, Partner and Admin level. | Done
2 | Observe the Company Name given in JIRA comments | Done | 2 | Observe the Company Name given in JIRA comments | Done
| STAGE |  |  | PRODUCTION
Login with Partner on Stage and Production simultaneously and start comparative testing
3 | Check for Company Access to Partner User, If access is not available then get it from Ashwin/Khandu/Leads | Done | 3 | Check for Company Access to Partner User, If access is not available then get it from Ashwin/Khandu/Leads | Done
4 | Go to 'Site Branding and Themes' page | Done | 4 | Go to 'Site Branding and Themes' page. - Compare and Apply the theme as on stage | Done
NOTE : (Do not chagne the theme until its mentioned explicitly)
5 | Go to Company Information tab | Done | 5 | Go to Company Information tab - Compare the Company Information Tab details and Save the Information page. | Done
NOTE : ( Confirm the Company Name displayed in Company Name field is same as mentioned in JIRA)
6 | Go to Company Contact Information tab | Pass | 6 | Go to Contact Information tab - Compare the Contact Information tab details with Stage. | Pass
7 | Go to System Settings tab | Pass | 7 | Go to System Settings tab - Compare the System Settings tab details with Stage. | Pass
8 | Go to Company Classes tab | Pass | 8 | Go to Company Classes tab - Compare the Company Classes tab details with Stage. | Pass |  | Test Classes observed in Class 2. Needs to be removed from production. BE Test NBE Test
9 | Go to Company Module Mapping tab | Pass | 9 | Go to Company Module Mapping tab - Compare and map the Module as on stage then click on Update button to save the mapped module(s). | Pass |  | Needs to be done on Main Company - DONE
10 | Go to New Hire/Rehire Rule tab | Pass | 10 | Go to New Hire/Rehire Rule tab - Compare the New Hire/Rehire Rules and eligibility settings. | Pass
11 | Go to Effective Date/Termination Date Rule tab | Pass | 11 | Go to Effective Date/Termination Date Rule tab - Compare the Effective Date/Termination Date Rules and eligibility settings. | Pass |  | Rule named "Delete Rule" is observed on production. Needs to be removed from production.
12 | Go to 'Employee Data Screen' tab | Pass | 12 | Go to 'Employee Data Screen' tab - Comapre with Stage and click on Save button to save the EDS. | Pass |  | Needs to be done on Main Company - DONE
13 | Customizer > Security | Pass | 13 | Customizer > Security - Compare Security Page settings with Stage | Pass
14 | Customizer > Dashboard Configuration | Pass | 14 | Customizer > Dashboard Configuration - Compare and Configure the Dashboard settings as that are on Stage | Pass |  | Needs to be done on Main Company - DONE
15 | Customizer > Rates | Pass | 15 | Customizer > Rates - Compare the Rates on Stage | Pass
16 | Customizer > Benefits Library > Add/Change Plan Design | Pass | 16 | Customizer > Benefits Library > Add/Change Plan Design - Compare the Plans,Count,Logs under each Benefit Type on Stage | Pass
17 | Customizer > Site Branding and Configurations | Pass | 17 | Customizer > Site Branding and Configurations - Compare settings with Stage | Pass |  | Needs to be done on Main Company - DONE
18 | Customizer > Employee Screen Configuration > Configure Landing Page | Pass | 18 | Customizer > Employee Screen Configuration > Configure Landing Page - Compare the Landing page Count, Text and Settings | Pass
19 | Employer Information > Payroll schedules | Pass | 19 | Employer Information > Payroll schedules - Comare the Payroll Schdules with Stage | Pass
20 | Add New Employee | Pass | 20 | Add New Employee | Pass
Login with Employee on Stage and Production simultaneously and start comparative testing
21 | Traverse the entire Self Serve Mode and list down the pages traversed | Pass | 21 | Traverse the entire Self Serve Mode and list down the pages traversed | Pass
22 | Employee Usage Agreement | Pass | 22 | Employee Usage Agreement | Pass
23 | Legal Agreement | Pass | 23 | Legal Agreement | Pass
24 | Landing Page | Pass | 24 | Landing Page | Pass
25 | Change Password | Pass | 25 | Change Password | Pass
27 | Demographics | Pass | 27 | Demographics | Pass
28 | Dependent Life Warning | Pass | 28 | Dependent Life Warning | Pass
29 | Spouse | Pass | 29 | Spouse | Pass
30 | Child | Pass | 30 | Child | Pass
31 | Enroll now - Medical | Pass | 31 | Enroll now - Medical | Pass
32 | Forms Library | Pass | 32 | Forms Library | NA |  | For HSPL copy, it does not work
33 | Benefit Description | Pass | 33 | Benefit Description | Pass
34 | Enroll Now - Dental | Pass | 34 | Enroll Now - Dental | Pass
35 | Enroll Now - Vision | Pass | 35 | Enroll Now - Vision | Pass
36 | Enroll Now - Supplemental Employee Life | Pass | 36 | Enroll Now - Supplemental Employee Life | Pass
37 | Enroll Now - Supplemental Employee AD&D | Pass | 37 | Enroll Now - Supplemental Employee AD&D | Pass
38 | Enroll Now - Supplemental Spouse Life | Pass | 38 | Enroll Now - Supplemental Spouse Life | Pass
39 | Enroll Now - Supplemental Spouse AD&D | Pass | 39 | Enroll Now - Supplemental Spouse AD&D | Pass
40 | Enroll Now - Supplemental Child Life | Pass | 40 | Enroll Now - Supplemental Child Life | Pass
41 | Enroll Now - Supplemental Child AD&D | Pass | 41 | Enroll Now - Supplemental Child AD&D | Pass
42 | Enroll Now - Short Term Disability | Pass | 42 | Enroll Now - Short Term Disability | Pass
43 | Enroll Now - Whole Life | Pass | 43 | Enroll Now - Whole Life | Pass
44 | Employee Beneficiary | Pass | 44 | Employee Beneficiary | Pass
45 | Upload Documents | Pass | 45 | Upload Documents | Pass
46 | Confirmation Statement | Pass | 46 | Confirmation Statement | Pass
47 | Employee Dashboard | Pass | 47 | Employee Dashboard | Pass
Login with Partner on Stage and Production simultaneously and start comparative testing
56 | Check for Admin Users | Pass | 56 | Check for Admin User. There should be no Admin User when Company is moved for First Time on Production | Pass
57 | Search for employee | Pass | 57 | Search for employee | Pass
58 | Manage Employee by partner | Pass | 58 | Manage Employee by partner | Pass
59 | Manage Employee by partner > Navigate different links when partner is managing employee (e.g. Medicare,Medicaid, Terminate as never effective, Coordination Benefits, Change Status, Primary Care Provider) | Pass | 59 | Manage Employee by partner > Navigate different links when partner is managing employee (e.g. Medicare,Medicaid, Terminate as never effective, Coordination Benefits, Change Status, Primary Care Provider) | Pass
60 | Partner Login > Reports | Pass | 60 | Partner Login > Reports | Pass
61 | Partner Login > Navigate different links under "Employee Administration" tab | Pass | 61 | Partner Login > Navigate different links under "Employee Administration" tab | Pass
62 | Partner Login > Navigate different links under "Employer Administration" tab | Pass | 62 | Partner Login > Navigate different links under "Employer Administration" tab | Pass
63 | Partner Login > Navigate different links under "Customizer" tab | Pass | 63 | Partner Login > Navigate different links under "Customizer" tab | Pass
64 | Partner Login > Navigate different links under "Import/Export" tab | Pass | 64 | Partner Login > Navigate different links under "Import/Export" tab | Pass
65 | Partner Login > Navigate different links under "Communication" tab | Pass | 65 | Partner Login > Navigate different links under "Communication" tab | Pass
Login with Admin on Stage and Production simultaneously and start comparative testing
66 | Check for Admin Users | Pass | 66 | Check for Admin User. There should be no Admin User when Company is moved for First Time on Production | Pass
67 | Search for employee | Pass | 67 | Search for employee | Pass
68 | Manage Employee by Admin | Pass | 68 | Manage Employee by Admin | Pass
69 | Manage Employee by partner > Navigate different links when partner is managing employee (e.g. Medicare,Medicaid, Terminate as never effective, Coordination Benefits, Change Status, Primary Care Provider) | Pass | 69 | Manage Employee by partner > Navigate different links when partner is managing employee (e.g. Medicare,Medicaid, Terminate as never effective, Coordination Benefits, Change Status, Primary Care Provider) | Pass
70 | Admin Login > Reports | Pass | 70 | Admin Login > Reports | Pass
71 | Admin Login > Navigate different links under "Employee Administration" tab | Pass | 71 | Admin Login > Navigate different links under "Employee Administration" tab | Pass
72 | Admin Login > Navigate different links under "Employer Administration" tab | Pass | 72 | Admin Login > Navigate different links under "Employer Administration" tab | Pass
73 | Admin Login > Navigate different links under "Customizer" tab | Pass | 73 | Admin Login > Navigate different links under "Customizer" tab | Pass
74 | Admin Login > Navigate different links under "Import/Export" tab | Pass | 74 | Admin Login > Navigate different links under "Import/Export" tab | Pass

## Email to Delete Test Data
Hi ……...,
Can you please delete following test employee from Production and Stage.
Sr.No. | Company | Environment | First Name | Last Name | SSN
1 | Optimum | Stage | Test | Hspl | 999999991 | hsplt9991
2 | Optimum for HSPL | Prod | Test | Hspl | 999999991 | hsplt9991