{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":7,"n_cols":3,"rows_kept":7,"flags":["formulas_cached_only"]}
["S.No.","Task description ","Hours"]
[1,"Analysis and discussion\nI) Mid month add/term in same plan with prorated policies\nii) Impact on adjustments with other policies\niii) Adjustment calculation approach \niv) Best approach finalization (after design team discussion)",10]
[2,"Coding\nI) Script changes in invoice Stored procedures\nii)DB structure changes",12]
[3,"Unit Testing\nI) Documenting the scenarios and Review\nii) Testing the scenarios",10]
[4,"Buffer",5]
[5,"Code and functionality review",3]
[null,"Total",40]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}